## Cover
NORTH PORT FIRE RESCUE
Strategic Plan · FY2026 – FY2029
MISSION
Provide exceptional public safety services in a safe, compassionate, and professional manner.
VISION
To be confirmed by command staff
VALUES
Trust · Family · Dedication · Compassion
STRATEGIC PILLARS
P1 | Operational Readiness and Deployment — Steward: Scott Lane (4/46 tasks, 9%)
P2 | Workforce Development and Succession — Steward: Nick Herlihy (11/71 tasks, 15%)
P3 | Community Risk Reduction and Public Education — Steward: Nick Satterly (5/44 tasks, 11%)
P4 | Professional Standards and Service Excellence — Steward: Rick Wilbert (12/55 tasks, 22%)
Generated June 14, 2026 · Restructured â€” 4 pillars, 12 domains

## Summary
STRATEGIC PLAN SUMMARY
Pillar | Name | Steward | Goals | Tasks | Done | Complete %
P1 | Operational Readiness and Deployment | Scott Lane | 10 | 46 | 4 | 8.696%
P2 | Workforce Development and Succession | Nick Herlihy | 16 | 71 | 11 | 15.49%
P3 | Community Risk Reduction and Public Education | Nick Satterly | 11 | 44 | 5 | 11.36%
P4 | Professional Standards and Service Excellence | Rick Wilbert | 12 | 55 | 12 | 21.82%
TOTAL |  |  |  | 216 | 32 | 14.81%

## By Year
GOALS BY FISCAL YEAR
FY26
Goal ID | Pillar | Goal Statement | Owner | Status | Success Metric
P1.26.G1 | Operational Readin | Develop and validate a comprehensive major incident response plan for each identified threat type within NPFR's response model, with at least one plan tested through a full-scale or functional drill by Q4. | TBD | In Progress | Major incident response plans validated through at least one full-scale or functional drill by Q4, with after-action documentation on file.
P1.26.G2 | Operational Readin | Develop and implement a comprehensive station facility maintenance monitoring program that identifies all high-use items by responsible party (Facilities or FD), establishes service and replacement schedules for each category, and creates an internal tracking system to ensure timely completion of all maintenance actions by Q4. | Kyle Dent | Not Started | Station facility maintenance monitoring program operational by Q4, with all items inventoried by responsible party, service schedules documented, and internal tracking system active.
P2.26.G1 | Workforce Developm | Develop and adopt a written department-wide succession plan that identifies all personnel eligible to separate within five years, maps critical position vacancies, and assigns developmental actions to identified successors by Q4. | TBD | In Progress | Written department-wide succession plan adopted by Q4, identifying all personnel eligible to separate within five years, mapping critical position vacancies, and assigning developmental actions to identified successors.
P2.26.G2 | Workforce Developm | Complete a full audit of the Officer Development Program, revise curriculum and job descriptions to reflect current competency expectations and CFAI credentialing categories, and relaunch with a documented delivery schedule by Q4. | TBD | In Progress | Revised Officer Development Program relaunched by Q4 with updated curriculum, current competency expectations aligned to CFAI credentialing categories, and a documented delivery schedule.
P2.26.G3 | Workforce Developm | Establish documented roles, responsibilities, and reporting structure for all training division positions, and implement a continuous evaluation framework for workload, span of control, and operational needs by Q3. | TBD | In Progress | Documented roles, responsibilities, and reporting structure established for all training division positions, and continuous evaluation framework for workload and span of control implemented by Q3.
P2.26.G4 | Workforce Developm | Implement a targeted recruitment program that includes formal partnerships with a minimum of four local technical schools, a functioning online recruitment portal, standardized interview questions, a documented scoring system, and an active recruitment committee by Q4. | TBD | Complete | Recruitment program operational by Q4 with formal partnerships at a minimum of four local technical schools, functioning online portal, standardized interview questions, documented scoring system, and active recruitment committee.
P3.26.G1 | Community Risk Red | Gather, organize, and evaluate community risk data from five sources including ImageTrend, police reporting, GIS, Mobile-Eyes, and regional data, and deliver a ranked baseline risk report identifying highest-priority program areas to the CRR team by Q2. | TBD | In Progress | Ranked baseline risk report identifying highest-priority program areas delivered to the CRR team by Q2, drawing from a minimum of five data sources.
P3.26.G2 | Community Risk Red | Design and launch two new community risk reduction programs targeting the highest-priority risk categories identified in the FY26 baseline report, including a formalized Elementary School CRR Education program and a Senior Public Education program, with both programs operational and baseline data collection underway by Q4. | TBD | In Progress | Elementary School CRR Education program and Senior Public Education program both operational by Q4, with baseline data collection underway for each.
P4.26.G1 | Professional Stand | Achieve CFAI accreditation candidate status by formalizing the Accreditation SOG, implementing compliant processes across all applicable categories, gathering documented proof of compliance, and submitting the CFAI candidate application by Q4. | TBD | In Progress | CFAI candidate application submitted by Q4, with Accreditation SOG formalized and documented proof of compliance gathered across all applicable categories.
P4.26.G2 | Professional Stand | Complete all ISO 1 annual compliance requirements including needs assessment, departmental collaboration, data documentation, and proof of compliance, and deliver a site visit readiness package by Q4. | TBD | Complete | ISO 1 annual compliance package complete by Q4, with all required data documented and site visit readiness package delivered.
P4.26.G3 | Professional Stand | Achieve the AHA Mission Lifeline Gold Rating by monitoring all required cardiac care metrics quarterly, verifying protocol alignment with current best practices, and submitting a complete Mission Lifeline application with supporting data by Q4. | TBD | Complete | Mission Lifeline Gold Rating application submitted by Q4 with supporting quarterly cardiac care data and protocol alignment verified.
FY27
Goal ID | Pillar | Goal Statement | Owner | Status | Success Metric
P1.27.G1 | Operational Readin | Increase the number of Hazardous Materials Technician-certified personnel by a minimum of three, establish a target hazard pre-plan library for all identified city sites, and conduct at least one HOT training or tabletop exercise by Q4. | Terry McCloud | Not Started | Minimum three additional Hazardous Materials Technician-certified personnel achieved, target hazard pre-plan library complete for all identified city sites, and at least one HOT training or tabletop exercise conducted by Q4.
P1.27.G2 | Operational Readin | Conduct a comprehensive PPE inventory assessment, establish minimum reserve inventory standards, develop a long-term lifecycle replacement model with annual funding projections, and implement a sustainable PPE readiness program by Q4. | TBD | Not Started | PPE inventory assessed, minimum reserve standards established, lifecycle replacement model documented with annual funding projections, and sustainable PPE readiness program implemented by Q4.
P1.27.G3 | Operational Readin | Evaluate the need for logistics resource hubs with locker technology at identified station locations, with installed inventory management systems, documented SOGs, trained personnel, and an initial effectiveness evaluation completed by Q4. | TBD | Not Started | Needs assessment complete, logistics resource hub program developed with inventory management system installed, SOGs documented, personnel trained, and initial effectiveness evaluation completed by Q4.
P2.27.G1 | Workforce Developm | Complete a comprehensive evaluation of EMS organizational span of control, staffing gaps, and succession needs including QA/QI, accreditation, and specialty program requirements, and present findings with specific recommendations to command staff by Q3. | TBD | Not Started | Comprehensive EMS organizational evaluation complete by Q3, with findings and specific staffing recommendations for QA/QI, accreditation, and specialty program positions presented to command staff.
P2.27.G2 | Workforce Developm | Conduct a comprehensive evaluation of training academy models, regional partnerships, and facility requirements to determine the feasibility and preferred approach for establishing an NPFR-hosted training academy, and present findings with a recommended implementation pathway to command staff by Q4. | TBD | Not Started | Feasibility report on NPFR-hosted training academy presented to command staff by Q4, with recommended implementation pathway, cost estimates, and regional partnership options documented.
P2.27.G3 | Workforce Developm | Complete a formal evaluation of sleep health challenges facing shift-based personnel, including review of current crew-quarters configuration, existing research on firefighter sleep deprivation, and peer agency solutions, and present findings with recommendations to command staff by Q4. | TBD | Not Started | Sleep health evaluation complete by Q4, with findings on crew-quarters configuration, personnel survey results, and facility and policy recommendations presented to command staff.
P2.27.G4 | Workforce Developm | Design and launch a structured internal communication program that establishes regular information flow between command staff and line personnel through scheduled station visits covering all stations at least twice annually, a quarterly department periodical, and a digital communication platform for shift-based staff, with all three components operational by Q4. | TBD | Not Started | Internal communication program fully operational by Q4, with all stations visited a minimum of twice, quarterly department periodical published, and digital communication platform active for shift-based staff.
P3.27.G1 | Community Risk Red | Analyze EMS incident data to identify priority community health risks, develop and launch targeted prevention initiatives addressing CPR, falls, stroke awareness, drowning prevention, and severe weather preparedness, and establish performance measures for all EMS-related CRR activities by Q3. | TBD | Not Started | Targeted EMS prevention initiatives addressing CPR, falls, stroke awareness, drowning prevention, and severe weather preparedness launched by Q3, with performance measures established for all EMS-related CRR activities.
P3.27.G2 | Community Risk Red | Develop a minimum of three new CRR program policies with supporting content by Q1, and complete phased rollout of a minimum of four CRR programs with Programs 1 and 2 operational by Q3 and Programs 3 and 4 operational by Q4. | TBD | Not Started | Minimum three new CRR program policies with supporting content complete by Q1, Programs 1 and 2 operational by Q3, and Programs 3 and 4 operational by Q4.
P3.27.G3 | Community Risk Red | Complete a CRR staffing capacity analysis relative to identified program delivery requirements, present a staffing needs recommendation to command staff by Q3, and establish interim capacity solutions including cross-training and volunteer engagement by Q4. | TBD | Not Started | CRR staffing capacity analysis presented to command staff by Q3, and interim capacity solutions including cross-training and volunteer engagement established by Q4.
P4.27.G1 | Professional Stand | Advance CFAI accreditation progress by completing all assigned tasks, incorporating 11th edition manual requirements, gathering ongoing proof of compliance across all categories, and reaching the next defined accreditation milestone by Q4. | TBD | Not Started | All assigned accreditation tasks completed, 11th edition manual requirements incorporated, and next defined CFAI accreditation milestone reached by Q4.
P4.27.G2 | Professional Stand | Complete CAAS re-accreditation by incorporating all 4th edition manual requirements, obtaining annual proofs of compliance across all applicable categories, submitting the re-accreditation application, and achieving a successful on-site review by Q4. | TBD | Not Started | CAAS re-accreditation achieved by Q4, with 4th edition manual requirements incorporated, all annual proofs of compliance gathered, re-accreditation application submitted, and successful on-site review conducted.
P4.27.G3 | Professional Stand | Complete an annual analysis of EMS response times, unit utilization, and call demand, map all EMS coverage gaps and high-demand response zones, evaluate rescue staffing models and resource allocation strategies, and present an ALS coverage improvement plan with specific recommendations to executive leadership by Q4. | TBD | Not Started | ALS coverage improvement plan with specific resource and staffing recommendations presented to executive leadership by Q4, based on completed response time analysis, coverage gap mapping, and staffing model evaluation.
FY28
Goal ID | Pillar | Goal Statement | Owner | Status | Success Metric
P1.28.G1 | Operational Readin | Develop and adopt a Logistics Division continuity plan that documents all critical functions, assigns position-specific continuity guides and SOPs, establishes a cross-training program covering all critical roles, and completes a program appraisal by Q4. | TBD | Not Started | Logistics Division continuity plan adopted with position-specific guides and SOPs for all critical functions, cross-training program established, and program appraisal completed by Q4.
P1.28.G2 | Operational Readin | Complete a structured assessment of all mutual aid and automatic aid agreements, radio interoperability, and CAD integration with primary mutual aid partners, and deliver a prioritized gap report to command staff by Q2. | TBD | Not Started | Structured assessment of all mutual aid agreements, radio interoperability, and CAD integration complete, with prioritized gap report delivered to command staff by Q2.
P1.28.G3 | Operational Readin | Develop updated mutual aid agreements, joint training protocols, and communications interoperability solutions addressing all gaps identified in the FY28 assessment, with all draft agreements delivered to partner agencies for review by Q4. | TBD | Not Started | Updated mutual aid agreements, joint training protocols, and communications interoperability solutions developed and delivered to all partner agencies for review by Q4.
P2.28.G1 | Workforce Developm | Complete a formal evaluation of EMS supervisory roles, field coverage effectiveness, and future deployment models, and present findings with implementation recommendations to command staff by Q4. | TBD | Not Started | EMS supervisory evaluation complete by Q4, with findings on field coverage effectiveness, clinical oversight opportunities, and implementation recommendations for future supervisory positions presented to command staff.
P2.28.G2 | Workforce Developm | Execute formal partnership agreements with a minimum of four regional educational institutions, establish documented shared-resource access protocols for training infrastructure, and develop a joint recruitment pipeline pathway with at least two institutions by Q4. | TBD | Not Started | Formal partnership agreements executed with a minimum of four regional educational institutions by Q4, shared-resource access protocols documented, and joint recruitment pipeline established with at least two institutions.
P2.28.G3 | Workforce Developm | Establish a functioning NPFR Training Academy by implementing the pathway recommended in the FY27 evaluation, securing necessary facility arrangements and partnerships, and delivering a minimum of one formally structured training program to internal personnel by Q4. | TBD | Not Started | NPFR Training Academy established by Q4, with facility and partnership agreements in place and a minimum of one formally structured training program delivered to internal personnel with outcomes documented.
P2.28.G4 | Workforce Developm | Implement the sleep health improvement recommendations identified in the FY27 sleep study, including retrofit of individual sleeping rooms at Brix station and adoption of station-level sleep hygiene protocols, with all primary facility modifications complete by Q4. | TBD | Not Started | Individual sleeping room retrofit at Brix station complete by Q4, station-level sleep hygiene protocols adopted, and personnel survey conducted to assess improvement in self-reported sleep quality.
P3.28.G1 | Community Risk Red | Gather updated CRR and EMS program data from all relevant sources, analyze incident trends to identify high-risk populations and areas, and deliver a written report documenting program strengths, weaknesses, and data-driven recommendations for program improvement by Q4. | TBD | Not Started | Written report documenting CRR and EMS program strengths, weaknesses, and data-driven improvement recommendations delivered by Q4, based on updated multi-source data analysis.
P3.28.G2 | Community Risk Red | Develop a Fire Explorer and Cadet pathway program in partnership with a minimum of two local high schools, conduct annual station visits and career days, and complete a formal program appraisal of the established Cadet Program by Q4. | TBD | Not Started | Fire Explorer and Cadet pathway program established in partnership with a minimum of two local high schools by Q4, annual station visits and career days implemented, and formal program appraisal of Cadet Program completed.
P3.28.G3 | Community Risk Red | Establish a Community Outreach Team of trained firefighters capable of supporting public education presentations and community events, with a defined team structure, trained membership, and a minimum of two community events delivered by Q4. | TBD | Not Started | Community Outreach Team established with defined structure and trained membership by Q4, and a minimum of two community events delivered.
P4.28.G1 | Professional Stand | Develop a centralized digital records management system including a complete record inventory, file mapping, access controls, migration of all active records not meeting retention, and completed disposition of records that have met retention requirements with the Clerk's office by Q4. | TBD | Not Started | Centralized digital records management system operational by Q4, with complete record inventory documented, all active records migrated, and records meeting retention requirements dispositioned with the Clerk's office.
P4.28.G2 | Professional Stand | Develop a Mobile Integrated Healthcare operational framework including target population analysis, partner identification, performance measures, referral pathways, and a financial and staffing feasibility evaluation, and present an MIH implementation recommendation to command staff by Q4. | TBD | Not Started | MIH implementation recommendation presented to command staff by Q4, with completed operational framework, target population analysis, partner identification, performance measures, referral pathways, and financial and staffing feasibility evaluation.
P4.28.G3 | Professional Stand | Evaluate the demand, financial viability, staffing requirements, and operational feasibility of a minimum of two advanced EMS service models, and present a prioritized implementation strategy with go/no-go recommendations to executive leadership by Q4. | TBD | Not Started | Prioritized implementation strategy with go/no-go recommendations for a minimum of two advanced EMS service models presented to executive leadership by Q4.
FY29
Goal ID | Pillar | Goal Statement | Owner | Status | Success Metric
P1.29.G1 | Operational Readin | Complete a fleet readiness and maintenance assessment that analyzes program effectiveness, calculates annual maintenance costs by apparatus, measures downtime against manufacturer PM schedules, identifies highest-burden units, and establishes KPIs for apparatus availability by Q4. | TBD | Not Started | Fleet readiness and maintenance assessment complete by Q4, with annual maintenance costs calculated per apparatus, downtime measured against manufacturer PM schedules, highest-burden units identified, and KPIs for apparatus availability established.
P1.29.G2 | Operational Readin | Execute signed updates to all mutual aid agreements, deliver a minimum of one joint interagency training exercise, and verify communications interoperability with all primary mutual aid partners by Q4. | TBD | Not Started | Signed updates to all mutual aid agreements executed, minimum one joint interagency training exercise delivered, and communications interoperability verified with all primary mutual aid partners by Q4.
P2.29.G1 | Workforce Developm | Achieve and document 90% or greater professional credentialing of all applicable positions aligned to CFAI credentialing categories, with individual completion plans in place for all remaining uncredentialed personnel by Q4. | TBD | Not Started | 90% or greater professional credentialing of all applicable positions documented by Q4, with individual completion plans on file for all remaining uncredentialed personnel.
P2.29.G2 | Workforce Developm | Develop and present a workforce growth plan that identifies staffing needs through FY32 based on call volume trends and community growth data, includes a phased onboarding model with hiring timeline, employment terms, career progression, and retention strategies, by Q4. | TBD | Not Started | Workforce growth plan presented to command staff by Q4, projecting staffing needs through FY32 with a phased onboarding model covering hiring timeline, employment terms, career progression, and retention strategies.
P2.29.G3 | Workforce Developm | Develop a financial plan addressing projected staffing growth needs through FY32, incorporating position cost modeling, identified funding sources, and a phased hiring timeline aligned to call volume thresholds, and present for command staff adoption by Q4. | TBD | Not Started | Financial plan addressing projected staffing growth through FY32 presented for command staff adoption by Q4, with position cost modeling, identified funding sources, and phased hiring timeline aligned to call volume thresholds.
P2.29.G4 | Workforce Developm | Achieve recognized training center status, host a minimum of two training sessions, increase collaborative training events with external agencies by 50% over the FY28 baseline, and increase external trainee participation in NPFR-led courses by 30% by Q4. | TBD | Not Started | Recognized training center status achieved, minimum two training sessions hosted, collaborative training events with external agencies increased 50% over FY28 baseline, and external trainee participation in NPFR-led courses increased 30% by Q4.
P3.29.G1 | Community Risk Red | Expand the three highest-performing CRR programs identified through FY28 data analysis by increasing reach, delivery frequency, or target population coverage, with documented expansion outcomes reported by Q2. | TBD | Not Started | Expansion of the three highest-performing CRR programs documented and reported by Q2, with measurable increases in reach, delivery frequency, or target population coverage.
P3.29.G2 | Community Risk Red | Implement targeted improvement plans for the three lowest-performing CRR programs identified through FY28 data analysis, with all improvement actions executed and outcomes assessed by Q3. | TBD | Not Started | Improvement plans for the three lowest-performing CRR programs implemented and outcomes assessed by Q3.
P3.29.G3 | Community Risk Red | Identify and address a minimum of two gaps in community outreach coverage targeting underserved geographic areas or demographic groups not currently reached by active CRR programs, with adapted or new program delivery operational in both identified gap areas by Q4. | TBD | Not Started | Adapted or new program delivery operational in a minimum of two identified underserved geographic areas or demographic gap populations by Q4.
P4.29.G1 | Professional Stand | Establish a Historical and Archive Committee with a formal mandate, recruited membership, and completed initial inventory of historical items by Q2, and implement agency performance standards with a documented compliance tracking and evaluation process by Q4. | TBD | Not Started | Historical and Archive Committee established with formal mandate, recruited membership, and initial inventory of historical items complete by Q2; agency performance standards implemented with documented compliance tracking process by Q4.
P4.29.G2 | Professional Stand | Implement the Mobile Integrated Healthcare program by establishing formal healthcare partnerships, completing all policy and documentation frameworks, launching a pilot serving identified high-utilizer or at-risk populations by Q4, and initiating quarterly outcomes tracking. | TBD | Not Started | MIH pilot program launched by Q4 serving identified high-utilizer or at-risk populations, with formal healthcare partnerships established, policy and documentation frameworks complete, and quarterly outcomes tracking initiated.
P4.29.G3 | Professional Stand | Implement a minimum of one advanced EMS service model based on FY28 feasibility findings with a documented operational framework, trained personnel, and structured outcomes tracking, and deliver a first-year performance report to command staff by Q4. | TBD | Not Started | Minimum one advanced EMS service model implemented by Q4, with documented operational framework, trained personnel, structured outcomes tracking, and first-year performance report delivered to command staff.

## P1 Operational Readines
P1 — Operational Readiness and Deployment
Steward: Scott Lane
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P1.26.G1 | FY26 | In Progress | — | Develop and validate a comprehensive major incident response plan for each identified threat type within NPFR's response model, with at least one plan tested through a full-scale or functional drill by Q4. | TBD | T1 | Identify major incident threat types across all hazard types. | Complete | Major incident response plans validated through at least one full-scale or functional drill by Q4, with after-action documentation on file.
[6 empty] | T2 | Develop a response plan for each identified threat. | Complete
[6 empty] | T3 | Plan and conduct a large-scale drill including active shooter scenario. | Complete
[6 empty] | T4 | Re-evaluate plans following drill and identify additional needs. | Complete
[6 empty] | T5 | Document plans and establish a regular review cycle. | Not Started
P1.26.G2 | FY26 | Not Started | — | Develop and implement a comprehensive station facility maintenance monitoring program that identifies all high-use items by responsible party (Facilities or FD), establishes service and replacement schedules for each category, and creates an internal tracking system to ensure timely completion of all maintenance actions by Q4. | Kyle Dent | T1 | Review and document items serviced by Facilities (A/C, garage doors, landscaping, etc.) and establish an internal monitoring process to track and prompt completion. | Not Started | Station facility maintenance monitoring program operational by Q4, with all items inventoried by responsible party, service schedules documented, and internal tracking system active.
[6 empty] | T2 | Identify and inventory all station items not covered by Facilities (stoves, ovens, mattresses, gym equipment, cascade systems, extractors, etc.) requiring FD-managed service schedules. | Not Started
[6 empty] | T3 | Explore service contracts with applicable vendors for FD-managed equipment and document service and replacement schedules for all identified items. | Not Started
[6 empty] | T4 | Develop a budget line item reflecting ongoing service and replacement costs for station equipment. | Not Started
FY27
P1.27.G1 | FY27 | Not Started | — | Increase the number of Hazardous Materials Technician-certified personnel by a minimum of three, establish a target hazard pre-plan library for all identified city sites, and conduct at least one HOT training or tabletop exercise by Q4. | Terry McCloud | T1 | Increase the number of personnel certified to the Hazardous Materials Technician level to serve as future Fire FTOs. | Not Started | Minimum three additional Hazardous Materials Technician-certified personnel achieved, target hazard pre-plan library complete for all identified city sites, and at least one HOT training or tabletop exercise conducted by Q4.
[6 empty] | T2 | Create a target hazard list for the city and develop incident response pre-plans for each site. | Not Started
[6 empty] | T3 | Conduct Hazmat targeted training. | Not Started
[6 empty] | T4 | Evaluate the need for additional equipment to effect safe response and mitigation. | Not Started
[6 empty] | T5 | Complete any needed policy updates. | Not Started
P1.27.G2 | FY27 | Not Started | — | Conduct a comprehensive PPE inventory assessment, establish minimum reserve inventory standards, develop a long-term lifecycle replacement model with annual funding projections, and implement a sustainable PPE readiness program by Q4. | TBD | T1 | Conduct a comprehensive assessment of the department's PPE inventory. | Not Started | PPE inventory assessed, minimum reserve standards established, lifecycle replacement model documented with annual funding projections, and sustainable PPE readiness program implemented by Q4.
[6 empty] | T2 | Develop minimum reserve PPE inventory standards. | Not Started
[6 empty] | T3 | Create a long-term PPE lifecycle replacement model. | Not Started
[6 empty] | T4 | Develop procedures. | Not Started
[6 empty] | T5 | Implement a sustainable PPE readiness program. | Not Started
P1.27.G3 ★ | FY27 | Not Started | — | Evaluate the need for logistics resource hubs with locker technology at identified station locations, with installed inventory management systems, documented SOGs, trained personnel, and an initial effectiveness evaluation completed by Q4. | TBD | T1 | Conduct a needs assessment and geographic analysis. | Not Started | Needs assessment complete, logistics resource hub program developed with inventory management system installed, SOGs documented, personnel trained, and initial effectiveness evaluation completed by Q4.
[6 empty] | T2 | Develop a Logistics Resource Hub program. | Not Started
[6 empty] | T3 | Purchase and install inventory management system. | Not Started
[6 empty] | T4 | Develop and implement standard operating guidelines and training for personnel. | Not Started
[6 empty] | T5 | Evaluate the effectiveness of the Logistics Resource Hub program. | Not Started
FY28
P1.28.G1 | FY28 | Not Started | P1.27.G3 | Develop and adopt a Logistics Division continuity plan that documents all critical functions, assigns position-specific continuity guides and SOPs, establishes a cross-training program covering all critical roles, and completes a program appraisal by Q4. | TBD | T1 | Identify critical logistics functions, systems, responsibilities, and operational processes. | Not Started | Logistics Division continuity plan adopted with position-specific guides and SOPs for all critical functions, cross-training program established, and program appraisal completed by Q4.
[6 empty] | T2 | Develop position-specific continuity guides and standard operating procedures for critical logistics functions. | Not Started
[6 empty] | T3 | Establish a cross-training program. | Not Started
[6 empty] | T4 | Develop a Logistics Division continuity plan. | Not Started
[6 empty] | T5 | Complete program appraisal. | Not Started
P1.28.G2 ★ | FY28 | Not Started | — | Complete a structured assessment of all mutual aid and automatic aid agreements, radio interoperability, and CAD integration with primary mutual aid partners, and deliver a prioritized gap report to command staff by Q2. | TBD | T1 | Compare mutual and automatic aid responses. | Not Started | Structured assessment of all mutual aid agreements, radio interoperability, and CAD integration complete, with prioritized gap report delivered to command staff by Q2.
[6 empty] | T2 | Review department ESZs for coverage and response alignment. | Not Started
[6 empty] | T3 | Assess radio and CAD interoperability with primary mutual aid partners. | Not Started
[6 empty] | T4 | Document findings and prioritize gaps by operational impact. | Not Started
P1.28.G3 ★ | FY28 | Not Started | P1.28.G2 | Develop updated mutual aid agreements, joint training protocols, and communications interoperability solutions addressing all gaps identified in the FY28 assessment, with all draft agreements delivered to partner agencies for review by Q4. | TBD | T1 | Collaborate with mutual aid partners on updated response procedures. | Not Started | Updated mutual aid agreements, joint training protocols, and communications interoperability solutions developed and delivered to all partner agencies for review by Q4.
[6 empty] | T2 | Formulate joint interagency training plans. | Not Started
[6 empty] | T3 | Identify technology or protocol solutions for interoperability gaps. | Not Started
[6 empty] | T4 | Draft updated mutual aid agreements where needed. | Not Started
FY29
P1.29.G1 | FY29 | Not Started | — | Complete a fleet readiness and maintenance assessment that analyzes program effectiveness, calculates annual maintenance costs by apparatus, measures downtime against manufacturer PM schedules, identifies highest-burden units, and establishes KPIs for apparatus availability by Q4. | TBD | T1 | Analyze maintenance program effectiveness and collect data to determine apparatus downtime. | Not Started | Fleet readiness and maintenance assessment complete by Q4, with annual maintenance costs calculated per apparatus, downtime measured against manufacturer PM schedules, highest-burden units identified, and KPIs for apparatus availability established.
[6 empty] | T2 | Compare PM schedule to that recommended by manufacturers. | Not Started
[6 empty] | T3 | Calculate annual maintenance cost for all apparatus and vehicles. | Not Started
[6 empty] | T4 | Identify which apparatus have the highest maintenance burden. | Not Started
[6 empty] | T5 | Create key performance indicators for apparatus availability rates. | Not Started
P1.29.G2 | FY29 | Not Started | P1.28.G3 | Execute signed updates to all mutual aid agreements, deliver a minimum of one joint interagency training exercise, and verify communications interoperability with all primary mutual aid partners by Q4. | TBD | T1 | Hold regular interagency coordination meetings. | Not Started | Signed updates to all mutual aid agreements executed, minimum one joint interagency training exercise delivered, and communications interoperability verified with all primary mutual aid partners by Q4.
[6 empty] | T2 | Formalize and execute updated mutual aid agreements. | Not Started
[6 empty] | T3 | Deliver at least one joint interagency training exercise. | Not Started
[6 empty] | T4 | Document outcomes and establish an annual review cycle. | Not Started

## P2 Workforce Developmen
P2 — Workforce Development and Succession
Steward: Nick Herlihy
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P2.26.G1 ★ | FY26 | In Progress | — | Develop and adopt a written department-wide succession plan that identifies all personnel eligible to separate within five years, maps critical position vacancies, and assigns developmental actions to identified successors by Q4. | TBD | T1 | Identify personnel leaving within the next five years. | Complete | Written department-wide succession plan adopted by Q4, identifying all personnel eligible to separate within five years, mapping critical position vacancies, and assigning developmental actions to identified successors.
[6 empty] | T2 | Develop written succession plan. | Not Started
[6 empty] | T3 | Review NFPA standards. | Not Started
[6 empty] | T4 | Survey local and regional departments. | Not Started
P2.26.G2 | FY26 | In Progress | — | Complete a full audit of the Officer Development Program, revise curriculum and job descriptions to reflect current competency expectations and CFAI credentialing categories, and relaunch with a documented delivery schedule by Q4. | TBD | T1 | Update and revise job descriptions. | Complete | Revised Officer Development Program relaunched by Q4 with updated curriculum, current competency expectations aligned to CFAI credentialing categories, and a documented delivery schedule.
[6 empty] | T2 | Develop education program. | Complete
[6 empty] | T3 | Collect and review feedback forms. | Complete
[6 empty] | T4 | Relaunch revised ODP with defined enrollment criteria and delivery schedule. | Not Started
P2.26.G3 | FY26 | In Progress | — | Establish documented roles, responsibilities, and reporting structure for all training division positions, and implement a continuous evaluation framework for workload, span of control, and operational needs by Q3. | TBD | T1 | Assess current staffing and workload distribution. | Complete | Documented roles, responsibilities, and reporting structure established for all training division positions, and continuous evaluation framework for workload and span of control implemented by Q3.
[6 empty] | T2 | Develop clear job descriptions and roles for specific training functions. | Complete
[6 empty] | T3 | Establish reporting structure for division oversight. | Not Started
[6 empty] | T4 | Implement a continuous evaluation process for workload and span of control. | Not Started
P2.26.G4 | FY26 | Complete | — | Implement a targeted recruitment program that includes formal partnerships with a minimum of four local technical schools, a functioning online recruitment portal, standardized interview questions, a documented scoring system, and an active recruitment committee by Q4. | TBD | T1 | Evaluate last fiscal year's applicant pool. | Complete | Recruitment program operational by Q4 with formal partnerships at a minimum of four local technical schools, functioning online portal, standardized interview questions, documented scoring system, and active recruitment committee.
[6 empty] | T2 | Partner with four local technical schools. | Complete
[6 empty] | T3 | Develop an online recruitment portal with QR code access. | Complete
[6 empty] | T4 | Develop standardized interview questions and a documented scoring system. | Complete
[6 empty] | T5 | Establish a recruitment committee. | Complete
FY27
P2.27.G1 ★ | FY27 | Not Started | — | Complete a comprehensive evaluation of EMS organizational span of control, staffing gaps, and succession needs including QA/QI, accreditation, and specialty program requirements, and present findings with specific recommendations to command staff by Q3. | TBD | T1 | Conduct comprehensive review of EMS span of control and organizational responsibilities by Q2. | Not Started | Comprehensive EMS organizational evaluation complete by Q3, with findings and specific staffing recommendations for QA/QI, accreditation, and specialty program positions presented to command staff.
[6 empty] | T2 | Evaluate staffing needs based on projected call volume growth and service demands by Q2. | Not Started
[6 empty] | T3 | Identify future staffing requirements for QA/QI, accreditation, MIH, and specialty programs by Q3. | Not Started
[6 empty] | T4 | Develop succession planning recommendations for EMS leadership positions by Q3. | Not Started
P2.27.G2 | FY27 | Not Started | P2.26.G1 | Conduct a comprehensive evaluation of training academy models, regional partnerships, and facility requirements to determine the feasibility and preferred approach for establishing an NPFR-hosted training academy, and present findings with a recommended implementation pathway to command staff by Q4. | TBD | T1 | Research existing training academy models at comparable agencies. | Not Started | Feasibility report on NPFR-hosted training academy presented to command staff by Q4, with recommended implementation pathway, cost estimates, and regional partnership options documented.
[6 empty] | T2 | Assess current NPFR training infrastructure, staffing, and resource gaps. | Not Started
[6 empty] | T3 | Evaluate regional partnership opportunities and shared-resource potential. | Not Started
[6 empty] | T4 | Develop feasibility report with cost estimates and recommended approach. | Not Started
[6 empty] | T5 | Present evaluation findings and recommended implementation pathway to command staff by Q4. | Not Started
P2.27.G3 ★ | FY27 | Not Started | — | Complete a formal evaluation of sleep health challenges facing shift-based personnel, including review of current crew-quarters configuration, existing research on firefighter sleep deprivation, and peer agency solutions, and present findings with recommendations to command staff by Q4. | TBD | T1 | Review current literature and peer agency practices on firefighter sleep health and shift-based sleep deprivation. | Not Started | Sleep health evaluation complete by Q4, with findings on crew-quarters configuration, personnel survey results, and facility and policy recommendations presented to command staff.
[6 empty] | T2 | Survey personnel to assess self-reported sleep quality and identified barriers within current station facilities. | Not Started
[6 empty] | T3 | Evaluate current crew-quarters configuration at each station for adequacy and improvement potential. | Not Started
[6 empty] | T4 | Identify facility and policy solutions including retrofit options, quiet-hour protocols, and scheduling adjustments. | Not Started
[6 empty] | T5 | Present sleep study findings and recommendations to command staff by Q4. | Not Started
P2.27.G4 | FY27 | Not Started | — | Design and launch a structured internal communication program that establishes regular information flow between command staff and line personnel through scheduled station visits covering all stations at least twice annually, a quarterly department periodical, and a digital communication platform for shift-based staff, with all three components operational by Q4. | TBD | T1 | Identify avenues for contact and exposure from officer to line personnel. | Not Started | Internal communication program fully operational by Q4, with all stations visited a minimum of twice, quarterly department periodical published, and digital communication platform active for shift-based staff.
[6 empty] | T2 | Explore creation of rotating schedule for all administrative officers to take turns visiting each station. | Not Started
[6 empty] | T3 | Design and launch a department periodical published at minimum quarterly. | Not Started
[6 empty] | T4 | Evaluate and implement a digital communication platform suitable for shift-based staff. | Not Started
[6 empty] | T5 | Assess program effectiveness at six and twelve months using personnel feedback. | Not Started
FY28
P2.28.G1 ★ | FY28 | Not Started | P2.27.G1 | Complete a formal evaluation of EMS supervisory roles, field coverage effectiveness, and future deployment models, and present findings with implementation recommendations to command staff by Q4. | TBD | T1 | Define EMS supervisor roles, responsibilities, and performance expectations by Q1. | Not Started | EMS supervisory evaluation complete by Q4, with findings on field coverage effectiveness, clinical oversight opportunities, and implementation recommendations for future supervisory positions presented to command staff.
[6 empty] | T2 | Evaluate field supervision coverage and operational effectiveness by Q2. | Not Started
[6 empty] | T3 | Assess opportunities for enhanced clinical oversight and workforce development by Q3. | Not Started
[6 empty] | T4 | Develop recommendations for future EMS supervisory positions and deployment models by Q3. | Not Started
[6 empty] | T5 | Present EMS supervisor evaluation findings and implementation recommendations by Q4. | Not Started
P2.28.G2 | FY28 | Not Started | — | Execute formal partnership agreements with a minimum of four regional educational institutions, establish documented shared-resource access protocols for training infrastructure, and develop a joint recruitment pipeline pathway with at least two institutions by Q4. | TBD | T1 | Strengthen relationships with decision makers at regional educational institutions. | Not Started | Formal partnership agreements executed with a minimum of four regional educational institutions by Q4, shared-resource access protocols documented, and joint recruitment pipeline established with at least two institutions.
[6 empty] | T2 | Establish or maintain articulation agreements with a minimum of four local institutions. | Not Started
[6 empty] | T3 | Inventory potential shared training resources including towers, props, and simulation equipment. | Not Started
[6 empty] | T4 | Develop protocols for shared resource access across partner institutions. | Not Started
P2.28.G3 ★ | FY28 | Not Started | — | Establish a functioning NPFR Training Academy by implementing the pathway recommended in the FY27 evaluation, securing necessary facility arrangements and partnerships, and delivering a minimum of one formally structured training program to internal personnel by Q4. | TBD | T1 | Implement facility and partnership agreements identified in FY27 evaluation. | Not Started | NPFR Training Academy established by Q4, with facility and partnership agreements in place and a minimum of one formally structured training program delivered to internal personnel with outcomes documented.
[6 empty] | T2 | Develop formal curriculum and delivery structure for inaugural training program. | Not Started
[6 empty] | T3 | Recruit and assign qualified training staff or adjunct instructors. | Not Started
[6 empty] | T4 | Deliver a minimum of one formally structured training program to NPFR personnel by Q4. | Not Started
[6 empty] | T5 | Document program outcomes and identify improvements for FY29 expansion. | Not Started
P2.28.G4 | FY28 | Not Started | P2.27.G3 | Implement the sleep health improvement recommendations identified in the FY27 sleep study, including retrofit of individual sleeping rooms at Brix station and adoption of station-level sleep hygiene protocols, with all primary facility modifications complete by Q4. | TBD | T1 | Develop project scope and cost estimate for Brix station individual room retrofit. | Not Started | Individual sleeping room retrofit at Brix station complete by Q4, station-level sleep hygiene protocols adopted, and personnel survey conducted to assess improvement in self-reported sleep quality.
[6 empty] | T2 | Secure funding and initiate facility retrofit at Brix station by Q2. | Not Started
[6 empty] | T3 | Develop and distribute station-level sleep hygiene protocols and wellness resources. | Not Started
[6 empty] | T4 | Complete primary facility modifications by Q4 and document outcomes. | Not Started
[6 empty] | T5 | Survey personnel post-implementation to assess improvement in self-reported sleep quality. | Not Started
FY29
P2.29.G1 | FY29 | Not Started | — | Achieve and document 90% or greater professional credentialing of all applicable positions aligned to CFAI credentialing categories, with individual completion plans in place for all remaining uncredentialed personnel by Q4. | TBD | T1 | Meet with all staff that have an associated CFAI credential category. | Not Started | 90% or greater professional credentialing of all applicable positions documented by Q4, with individual completion plans on file for all remaining uncredentialed personnel.
[6 empty] | T2 | Integrate in the department succession plan document. | Not Started
[6 empty] | T3 | Develop an individual plan for completion for all staff as applicable. | Not Started
[6 empty] | T4 | Incorporate into the NPFR Officer Development Program. | Not Started
P2.29.G2 | FY29 | Not Started | P2.28.G1 | Develop and present a workforce growth plan that identifies staffing needs through FY32 based on call volume trends and community growth data, includes a phased onboarding model with hiring timeline, employment terms, career progression, and retention strategies, by Q4. | TBD | T1 | Analyze population demographics, call volume trends, and urban vs rural growth projections. | Not Started | Workforce growth plan presented to command staff by Q4, projecting staffing needs through FY32 with a phased onboarding model covering hiring timeline, employment terms, career progression, and retention strategies.
[6 empty] | T2 | Identify emerging staffing needs across all divisions through FY32. | Not Started
[6 empty] | T3 | Develop a phased onboarding plan including hiring, employment terms, career progression, and retention strategies. | Not Started
[6 empty] | T4 | Present workforce growth plan to command staff with supporting data. | Not Started
P2.29.G3 | FY29 | Not Started | P2.28.G1 | Develop a financial plan addressing projected staffing growth needs through FY32, incorporating position cost modeling, identified funding sources, and a phased hiring timeline aligned to call volume thresholds, and present for command staff adoption by Q4. | TBD | T1 | Consider grants and identify available funding sources. | Not Started | Financial plan addressing projected staffing growth through FY32 presented for command staff adoption by Q4, with position cost modeling, identified funding sources, and phased hiring timeline aligned to call volume thresholds.
[6 empty] | T2 | Calculate base salaries for projected future positions. | Not Started
[6 empty] | T3 | Develop phased budget request aligned to hiring timeline. | Not Started
P2.29.G4 | FY29 | Not Started | P2.28.G3 | Achieve recognized training center status, host a minimum of two training sessions, increase collaborative training events with external agencies by 50% over the FY28 baseline, and increase external trainee participation in NPFR-led courses by 30% by Q4. | TBD | T1 | Ensure accreditation requirements are met and submit necessary applications. | Not Started | Recognized training center status achieved, minimum two training sessions hosted, collaborative training events with external agencies increased 50% over FY28 baseline, and external trainee participation in NPFR-led courses increased 30% by Q4.
[6 empty] | T2 | Host a minimum of two accredited training sessions within the fiscal year. | Not Started
[6 empty] | T3 | Establish joint training agreements targeting a 50% increase in collaborative events. | Not Started
[6 empty] | T4 | Develop promotional materials and an online portal to increase external trainee participation by 30%. | Not Started
[6 empty] | T5 | Host one regional training symposium. | Not Started

## P3 Community Risk Reduc
P3 — Community Risk Reduction and Public Education
Steward: Nick Satterly
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P3.26.G1 ★ | FY26 | In Progress | — | Gather, organize, and evaluate community risk data from five sources including ImageTrend, police reporting, GIS, Mobile-Eyes, and regional data, and deliver a ranked baseline risk report identifying highest-priority program areas to the CRR team by Q2. | TBD | T1 | Access and compile data from ImageTrend, police reporting, GIS, Mobile-Eyes, and regional sources. | Complete | Ranked baseline risk report identifying highest-priority program areas delivered to the CRR team by Q2, drawing from a minimum of five data sources.
[6 empty] | T2 | Organize data and rank by importance, financial impact, and organizational capacity. | Complete
[6 empty] | T3 | Evaluate data to identify highest-priority risk areas for program development. | Not Started
[6 empty] | T4 | Document baseline findings and present to CRR team. | Not Started
P3.26.G2 | FY26 | In Progress | P3.26.G1 | Design and launch two new community risk reduction programs targeting the highest-priority risk categories identified in the FY26 baseline report, including a formalized Elementary School CRR Education program and a Senior Public Education program, with both programs operational and baseline data collection underway by Q4. | TBD | T1 | Establish programs based on greatest identified need from data evaluation. | Complete | Elementary School CRR Education program and Senior Public Education program both operational by Q4, with baseline data collection underway for each.
[6 empty] | T2 | Formalize Elementary School CRR Education program. | Complete
[6 empty] | T3 | Formalize Senior Public Education program. | Complete
[6 empty] | T4 | Formalize SOGs for Fire Marshal program delivery. | Not Started
FY27
P3.27.G1 | FY27 | Not Started | — | Analyze EMS incident data to identify priority community health risks, develop and launch targeted prevention initiatives addressing CPR, falls, stroke awareness, drowning prevention, and severe weather preparedness, and establish performance measures for all EMS-related CRR activities by Q3. | TBD | T1 | Analyze EMS incident data to identify priority community health risks by Q1. | Not Started | Targeted EMS prevention initiatives addressing CPR, falls, stroke awareness, drowning prevention, and severe weather preparedness launched by Q3, with performance measures established for all EMS-related CRR activities.
[6 empty] | T2 | Develop targeted prevention initiatives addressing CPR, falls, stroke awareness, drowning prevention, and severe weather preparedness by Q2. | Not Started
[6 empty] | T3 | Strengthen partnerships with hospitals and community organizations by Q2. | Not Started
[6 empty] | T4 | Establish performance measures to evaluate EMS-related CRR activities by Q3. | Not Started
[6 empty] | T5 | Complete annual review to ensure outreach efforts align with identified community risks by Q4. | Not Started
P3.27.G2 ★ | FY27 | Not Started | P3.26.G1 | Develop a minimum of three new CRR program policies with supporting content by Q1, and complete phased rollout of a minimum of four CRR programs with Programs 1 and 2 operational by Q3 and Programs 3 and 4 operational by Q4. | TBD | T1 | Build out three new CRR program policies and supporting content by Q1. | Not Started | Minimum three new CRR program policies with supporting content complete by Q1, Programs 1 and 2 operational by Q3, and Programs 3 and 4 operational by Q4.
[6 empty] | T2 | Identify staffing requirements and incorporate scheduling for program delivery. | Not Started
[6 empty] | T3 | Implement Programs 1 and 2 by Q3. | Not Started
[6 empty] | T4 | Implement Programs 3 and 4 by Q4. | Not Started
P3.27.G3 ★ | FY27 | Not Started | — | Complete a CRR staffing capacity analysis relative to identified program delivery requirements, present a staffing needs recommendation to command staff by Q3, and establish interim capacity solutions including cross-training and volunteer engagement by Q4. | TBD | T1 | Review CRR program workload against identified community risk priorities. | Not Started | CRR staffing capacity analysis presented to command staff by Q3, and interim capacity solutions including cross-training and volunteer engagement established by Q4.
[6 empty] | T2 | Evaluate current staffing capacity against program delivery requirements. | Not Started
[6 empty] | T3 | Develop a staffing needs analysis identifying positions required for full program implementation. | Not Started
[6 empty] | T4 | Submit staffing request through appropriate budget and HR channels if confirmed. | Not Started
[6 empty] | T5 | Establish interim capacity solutions including cross-training and volunteer engagement. | Not Started
FY28
P3.28.G1 ★ | FY28 | Not Started | P3.27.G2 | Gather updated CRR and EMS program data from all relevant sources, analyze incident trends to identify high-risk populations and areas, and deliver a written report documenting program strengths, weaknesses, and data-driven recommendations for program improvement by Q4. | TBD | T1 | Access data from ImageTrend, CARES database, GIS, regional sources, and external surveys. | Not Started | Written report documenting CRR and EMS program strengths, weaknesses, and data-driven improvement recommendations delivered by Q4, based on updated multi-source data analysis.
[6 empty] | T2 | Analyze EMS incident data to identify high-risk areas and vulnerable populations. | Not Started
[6 empty] | T3 | Compare previous data to current to identify program performance markers. | Not Started
[6 empty] | T4 | Research and document program strengths and weaknesses for reporting. | Not Started
P3.28.G2 | FY28 | Not Started | — | Develop a Fire Explorer and Cadet pathway program in partnership with a minimum of two local high schools, conduct annual station visits and career days, and complete a formal program appraisal of the established Cadet Program by Q4. | TBD | T1 | Develop a Fire Explorer/Cadet pathway with local high schools. | Not Started | Fire Explorer and Cadet pathway program established in partnership with a minimum of two local high schools by Q4, annual station visits and career days implemented, and formal program appraisal of Cadet Program completed.
[6 empty] | T2 | Create annual station visits and career days for students. | Not Started
[6 empty] | T3 | Complete program appraisal for established Cadet Program. | Not Started
[6 empty] | T4 | Explore Summer Camp concept. | Not Started
[6 empty] | T5 | Analyze for potential financial impacts or needs. | Not Started
P3.28.G3 | FY28 | Not Started | P3.27.G3 | Establish a Community Outreach Team of trained firefighters capable of supporting public education presentations and community events, with a defined team structure, trained membership, and a minimum of two community events delivered by Q4. | TBD | T1 | Train firefighters interested in public education. | Not Started | Community Outreach Team established with defined structure and trained membership by Q4, and a minimum of two community events delivered.
[6 empty] | T2 | Create a group of dedicated members who can assist with presentations and events. | Not Started
[6 empty] | T3 | Analyze impact of line personnel engaged in CRR activities both internally and externally. | Not Started
[6 empty] | T4 | Evaluate the potential of using retired firefighters as volunteers. | Not Started
FY29
P3.29.G1 | FY29 | Not Started | P3.28.G1 | Expand the three highest-performing CRR programs identified through FY28 data analysis by increasing reach, delivery frequency, or target population coverage, with documented expansion outcomes reported by Q2. | TBD | T1 | Identify the three programs with strongest performance data. | Not Started | Expansion of the three highest-performing CRR programs documented and reported by Q2, with measurable increases in reach, delivery frequency, or target population coverage.
[6 empty] | T2 | Expand upon proven strengths in reach, impact, and delivery. | Not Started
P3.29.G2 | FY29 | Not Started | P3.28.G1 | Implement targeted improvement plans for the three lowest-performing CRR programs identified through FY28 data analysis, with all improvement actions executed and outcomes assessed by Q3. | TBD | T1 | Identify three programs with weakest performance data. | Not Started | Improvement plans for the three lowest-performing CRR programs implemented and outcomes assessed by Q3.
[6 empty] | T2 | Discuss and list specific ways to improve each program. | Not Started
[6 empty] | T3 | Implement improvement plans for all three programs by Q3. | Not Started
P3.29.G3 | FY29 | Not Started | — | Identify and address a minimum of two gaps in community outreach coverage targeting underserved geographic areas or demographic groups not currently reached by active CRR programs, with adapted or new program delivery operational in both identified gap areas by Q4. | TBD | T1 | Identify two underserved geographic areas or demographic groups with no active program coverage. | Not Started | Adapted or new program delivery operational in a minimum of two identified underserved geographic areas or demographic gap populations by Q4.
[6 empty] | T2 | Prioritize outreach gaps based on risk profile and feasibility of delivery. | Not Started
[6 empty] | T3 | Develop or adapt program delivery models appropriate for each gap population. | Not Started
[6 empty] | T4 | Launch adapted or new delivery in both identified gap areas by Q4. | Not Started

## P4 Professional Standar
P4 — Professional Standards and Service Excellence
Steward: Rick Wilbert
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P4.26.G1 ★ | FY26 | In Progress | — | Achieve CFAI accreditation candidate status by formalizing the Accreditation SOG, implementing compliant processes across all applicable categories, gathering documented proof of compliance, and submitting the CFAI candidate application by Q4. | TBD | T1 | Strategic Plan adopted by the AHJ | Not Started | CFAI candidate application submitted by Q4, with Accreditation SOG formalized and documented proof of compliance gathered across all applicable categories.
[6 empty] | T2 | Implement processes and move toward best practice alignment. | Complete
[6 empty] | T3 | Gather proof of compliance. | Complete
[6 empty] | T4 | Achieve CFAI applicant status. | Complete
[6 empty] | T5 | CRA SOC Adopted by the AHJ | Not Started
P4.26.G2 | FY26 | Complete | — | Complete all ISO 1 annual compliance requirements including needs assessment, departmental collaboration, data documentation, and proof of compliance, and deliver a site visit readiness package by Q4. | TBD | T1 | Review all criteria required to maintain ISO 1. | Complete | ISO 1 annual compliance package complete by Q4, with all required data documented and site visit readiness package delivered.
[6 empty] | T2 | Assess organizational needs against ISO requirements. | Complete
[6 empty] | T3 | Assign needs and collaborate with other departments. | Complete
[6 empty] | T4 | Document all required data and proof of compliance. | Complete
[6 empty] | T5 | Prepare for ISO site visit. | Complete
P4.26.G3 | FY26 | Complete | — | Achieve the AHA Mission Lifeline Gold Rating by monitoring all required cardiac care metrics quarterly, verifying protocol alignment with current best practices, and submitting a complete Mission Lifeline application with supporting data by Q4. | TBD | T1 | Monitor current and future metrics. | Complete | Mission Lifeline Gold Rating application submitted by Q4 with supporting quarterly cardiac care data and protocol alignment verified.
[6 empty] | T2 | Ensure protocols continue to meet best practices. | Complete
[6 empty] | T3 | Quarterly reporting of data. | Complete
[6 empty] | T4 | Submit measures for Mission Lifeline Gold Rating evaluation. | Complete
FY27
P4.27.G1 ★ | FY27 | Not Started | P4.26.G1 | Advance CFAI accreditation progress by completing all assigned tasks, incorporating 11th edition manual requirements, gathering ongoing proof of compliance across all categories, and reaching the next defined accreditation milestone by Q4. | TBD | T1 | Follow up on all currently assigned accreditation tasks. | Not Started | All assigned accreditation tasks completed, 11th edition manual requirements incorporated, and next defined CFAI accreditation milestone reached by Q4.
[6 empty] | T2 | Implement processes and continue moving toward best practice alignment. | Not Started
[6 empty] | T3 | Gather ongoing proof of compliance. | Not Started
[6 empty] | T4 | Incorporate 11th edition manual requirements. | Not Started
P4.27.G2 | FY27 | Not Started | — | Complete CAAS re-accreditation by incorporating all 4th edition manual requirements, obtaining annual proofs of compliance across all applicable categories, submitting the re-accreditation application, and achieving a successful on-site review by Q4. | TBD | T1 | Review CAAS 4th edition manual requirements and identify all applicable changes from the previous accreditation cycle. | Not Started | CAAS re-accreditation achieved by Q4, with 4th edition manual requirements incorporated, all annual proofs of compliance gathered, re-accreditation application submitted, and successful on-site review conducted.
[6 empty] | T2 | Conduct an internal gap assessment comparing current processes and documentation to 4th edition standards. | Not Started
[6 empty] | T3 | Gather and organize annual proofs of compliance for all required CAAS categories. | Not Started
[6 empty] | T4 | Prepare and submit CAAS re-accreditation application by Q3. | Not Started
[6 empty] | T5 | Conduct internal pre-site-visit readiness review, address identified deficiencies, and prepare staff for on-site evaluation. | Not Started
P4.27.G3 | FY27 | Not Started | — | Complete an annual analysis of EMS response times, unit utilization, and call demand, map all EMS coverage gaps and high-demand response zones, evaluate rescue staffing models and resource allocation strategies, and present an ALS coverage improvement plan with specific recommendations to executive leadership by Q4. | TBD | T1 | Complete annual analysis of EMS response times, unit utilization, and call demand by Q2. | Not Started | ALS coverage improvement plan with specific resource and staffing recommendations presented to executive leadership by Q4, based on completed response time analysis, coverage gap mapping, and staffing model evaluation.
[6 empty] | T2 | Identify and map EMS coverage gaps and high demand response zones by Q2. | Not Started
[6 empty] | T3 | Evaluate rescue staffing models and resource allocation strategies by Q3. | Not Started
[6 empty] | T4 | Present ALS coverage improvement plan to executive leadership by Q4. | Not Started
FY28
P4.28.G1 | FY28 | Not Started | — | Develop a centralized digital records management system including a complete record inventory, file mapping, access controls, migration of all active records not meeting retention, and completed disposition of records that have met retention requirements with the Clerk's office by Q4. | TBD | T1 | Meet with staff to develop record inventory. | Not Started | Centralized digital records management system operational by Q4, with complete record inventory documented, all active records migrated, and records meeting retention requirements dispositioned with the Clerk's office.
[6 empty] | T2 | Develop record library system. | Not Started
[6 empty] | T3 | Migrate records that have not met retention to centralized record library. | Not Started
[6 empty] | T4 | Inventory electronic records having met retention, review with staff, and complete necessary disposals with the Clerk's office. | Not Started
P4.28.G2 ★ | FY28 | Not Started | — | Develop a Mobile Integrated Healthcare operational framework including target population analysis, partner identification, performance measures, referral pathways, and a financial and staffing feasibility evaluation, and present an MIH implementation recommendation to command staff by Q4. | TBD | T1 | Analyze EMS incident data to identify target populations and service gaps by Q2. | Not Started | MIH implementation recommendation presented to command staff by Q4, with completed operational framework, target population analysis, partner identification, performance measures, referral pathways, and financial and staffing feasibility evaluation.
[6 empty] | T2 | Identify potential healthcare and community partners for MIH program collaboration by Q2. | Not Started
[6 empty] | T3 | Develop MIH operational framework, performance measures, and referral pathways by Q3. | Not Started
[6 empty] | T4 | Evaluate financial, staffing, and regulatory requirements for program implementation by Q3. | Not Started
[6 empty] | T5 | Present MIH feasibility study and implementation recommendations by Q4. | Not Started
P4.28.G3 ★ | FY28 | Not Started | — | Evaluate the demand, financial viability, staffing requirements, and operational feasibility of a minimum of two advanced EMS service models, and present a prioritized implementation strategy with go/no-go recommendations to executive leadership by Q4. | TBD | T1 | Evaluate demand and operational feasibility for specialty care transport services by Q2. | Not Started | Prioritized implementation strategy with go/no-go recommendations for a minimum of two advanced EMS service models presented to executive leadership by Q4.
[6 empty] | T2 | Analyze reimbursement opportunities and financial impacts of advanced EMS programs by Q3. | Not Started
[6 empty] | T3 | Identify staffing, training, credentialing, and equipment requirements for advanced EMS services by Q3. | Not Started
[6 empty] | T4 | Develop operational frameworks and response criteria for potential advanced EMS programs by Q4. | Not Started
[6 empty] | T5 | Present implementation recommendations and prioritization strategy to executive leadership by Q4. | Not Started
FY29
P4.29.G1 | FY29 | Not Started | P4.27.G1 | Establish a Historical and Archive Committee with a formal mandate, recruited membership, and completed initial inventory of historical items by Q2, and implement agency performance standards with a documented compliance tracking and evaluation process by Q4. | TBD | T1 | Develop committee mandate, scope, mission, goals. | Not Started | Historical and Archive Committee established with formal mandate, recruited membership, and initial inventory of historical items complete by Q2; agency performance standards implemented with documented compliance tracking process by Q4.
[6 empty] | T2 | Establish structure and roles. | Not Started
[6 empty] | T3 | Identify potential members and recruit. | Not Started
[6 empty] | T4 | Develop appropriate policies and procedures. | Not Started
[6 empty] | T5 | Inventory and evaluate existing items. | Not Started
[6 empty] | T6 | Implement agency performance standards and develop a compliance tracking process. | Not Started
P4.29.G2 | FY29 | Not Started | P4.28.G2 | Implement the Mobile Integrated Healthcare program by establishing formal healthcare partnerships, completing all policy and documentation frameworks, launching a pilot serving identified high-utilizer or at-risk populations by Q4, and initiating quarterly outcomes tracking. | TBD | T1 | Establish formal partnerships with healthcare providers and community organizations by Q2. | Not Started | MIH pilot program launched by Q4 serving identified high-utilizer or at-risk populations, with formal healthcare partnerships established, policy and documentation frameworks complete, and quarterly outcomes tracking initiated.
[6 empty] | T2 | Develop MIH policies, procedures, and documentation standards by Q3. | Not Started
[6 empty] | T3 | Implement MIH pilot program serving identified high-utilizer or at-risk populations by Q4. | Not Started
[6 empty] | T4 | Track patient outcomes, EMS utilization impacts, and program effectiveness quarterly. | Not Started
P4.29.G3 | FY29 | Not Started | P4.28.G3 | Implement a minimum of one advanced EMS service model based on FY28 feasibility findings with a documented operational framework, trained personnel, and structured outcomes tracking, and deliver a first-year performance report to command staff by Q4. | TBD | T1 | Establish Specialty Care Transport framework. | Not Started | Minimum one advanced EMS service model implemented by Q4, with documented operational framework, trained personnel, structured outcomes tracking, and first-year performance report delivered to command staff.
[6 empty] | T2 | Train specialty transport personnel. | Not Started
[6 empty] | T3 | Implement at least one advanced EMS program or pilot initiative by Q4. | Not Started
[6 empty] | T4 | Measure operational, clinical, and financial outcomes and report findings annually. | Not Started

## Dependencies
DEPENDENCY CHAINS
★ = Gate goal — must complete before downstream goals can begin
Gate Goal | Gate Statement | Unlocks | Unlocked Statement
P1.27.G3 ★ | Evaluate the need for logistics resource hubs with locker technology at identified station locations, with installed inventory management systems, documented SOGs, trained personnel, and an initial effectiveness evaluation completed by Q4. | P1.28.G1 | Develop and adopt a Logistics Division continuity plan that documents all critical functions, assigns position-specific continuity guides and SOPs, establishes a cross-training program covering all critical roles, and completes a program appraisal by Q4.
P1.28.G2 ★ | Complete a structured assessment of all mutual aid and automatic aid agreements, radio interoperability, and CAD integration with primary mutual aid partners, and deliver a prioritized gap report to command staff by Q2. | P1.28.G3 | Develop updated mutual aid agreements, joint training protocols, and communications interoperability solutions addressing all gaps identified in the FY28 assessment, with all draft agreements delivered to partner agencies for review by Q4.
P1.28.G3 ★ | Develop updated mutual aid agreements, joint training protocols, and communications interoperability solutions addressing all gaps identified in the FY28 assessment, with all draft agreements delivered to partner agencies for review by Q4. | P1.29.G2 | Execute signed updates to all mutual aid agreements, deliver a minimum of one joint interagency training exercise, and verify communications interoperability with all primary mutual aid partners by Q4.
P2.26.G1 ★ | Develop and adopt a written department-wide succession plan that identifies all personnel eligible to separate within five years, maps critical position vacancies, and assigns developmental actions to identified successors by Q4. | P2.27.G2 | Conduct a comprehensive evaluation of training academy models, regional partnerships, and facility requirements to determine the feasibility and preferred approach for establishing an NPFR-hosted training academy, and present findings with a recommended implementation pathway to command staff by Q4.
P2.27.G1 ★ | Complete a comprehensive evaluation of EMS organizational span of control, staffing gaps, and succession needs including QA/QI, accreditation, and specialty program requirements, and present findings with specific recommendations to command staff by Q3. | P2.28.G1 | Complete a formal evaluation of EMS supervisory roles, field coverage effectiveness, and future deployment models, and present findings with implementation recommendations to command staff by Q4.
P2.27.G3 ★ | Complete a formal evaluation of sleep health challenges facing shift-based personnel, including review of current crew-quarters configuration, existing research on firefighter sleep deprivation, and peer agency solutions, and present findings with recommendations to command staff by Q4. | P2.28.G4 | Implement the sleep health improvement recommendations identified in the FY27 sleep study, including retrofit of individual sleeping rooms at Brix station and adoption of station-level sleep hygiene protocols, with all primary facility modifications complete by Q4.
P2.28.G1 ★ | Complete a formal evaluation of EMS supervisory roles, field coverage effectiveness, and future deployment models, and present findings with implementation recommendations to command staff by Q4. | P2.29.G2 | Develop and present a workforce growth plan that identifies staffing needs through FY32 based on call volume trends and community growth data, includes a phased onboarding model with hiring timeline, employment terms, career progression, and retention strategies, by Q4.
P2.28.G1 ★ | Complete a formal evaluation of EMS supervisory roles, field coverage effectiveness, and future deployment models, and present findings with implementation recommendations to command staff by Q4. | P2.29.G3 | Develop a financial plan addressing projected staffing growth needs through FY32, incorporating position cost modeling, identified funding sources, and a phased hiring timeline aligned to call volume thresholds, and present for command staff adoption by Q4.
P2.28.G3 ★ | Establish a functioning NPFR Training Academy by implementing the pathway recommended in the FY27 evaluation, securing necessary facility arrangements and partnerships, and delivering a minimum of one formally structured training program to internal personnel by Q4. | P2.29.G4 | Achieve recognized training center status, host a minimum of two training sessions, increase collaborative training events with external agencies by 50% over the FY28 baseline, and increase external trainee participation in NPFR-led courses by 30% by Q4.
P3.26.G1 ★ | Gather, organize, and evaluate community risk data from five sources including ImageTrend, police reporting, GIS, Mobile-Eyes, and regional data, and deliver a ranked baseline risk report identifying highest-priority program areas to the CRR team by Q2. | P3.26.G2 | Design and launch two new community risk reduction programs targeting the highest-priority risk categories identified in the FY26 baseline report, including a formalized Elementary School CRR Education program and a Senior Public Education program, with both programs operational and baseline data collection underway by Q4.
P3.26.G1 ★ | Gather, organize, and evaluate community risk data from five sources including ImageTrend, police reporting, GIS, Mobile-Eyes, and regional data, and deliver a ranked baseline risk report identifying highest-priority program areas to the CRR team by Q2. | P3.27.G2 | Develop a minimum of three new CRR program policies with supporting content by Q1, and complete phased rollout of a minimum of four CRR programs with Programs 1 and 2 operational by Q3 and Programs 3 and 4 operational by Q4.
P3.27.G2 ★ | Develop a minimum of three new CRR program policies with supporting content by Q1, and complete phased rollout of a minimum of four CRR programs with Programs 1 and 2 operational by Q3 and Programs 3 and 4 operational by Q4. | P3.28.G1 | Gather updated CRR and EMS program data from all relevant sources, analyze incident trends to identify high-risk populations and areas, and deliver a written report documenting program strengths, weaknesses, and data-driven recommendations for program improvement by Q4.
P3.27.G3 ★ | Complete a CRR staffing capacity analysis relative to identified program delivery requirements, present a staffing needs recommendation to command staff by Q3, and establish interim capacity solutions including cross-training and volunteer engagement by Q4. | P3.28.G3 | Establish a Community Outreach Team of trained firefighters capable of supporting public education presentations and community events, with a defined team structure, trained membership, and a minimum of two community events delivered by Q4.
P3.28.G1 ★ | Gather updated CRR and EMS program data from all relevant sources, analyze incident trends to identify high-risk populations and areas, and deliver a written report documenting program strengths, weaknesses, and data-driven recommendations for program improvement by Q4. | P3.29.G1 | Expand the three highest-performing CRR programs identified through FY28 data analysis by increasing reach, delivery frequency, or target population coverage, with documented expansion outcomes reported by Q2.
P3.28.G1 ★ | Gather updated CRR and EMS program data from all relevant sources, analyze incident trends to identify high-risk populations and areas, and deliver a written report documenting program strengths, weaknesses, and data-driven recommendations for program improvement by Q4. | P3.29.G2 | Implement targeted improvement plans for the three lowest-performing CRR programs identified through FY28 data analysis, with all improvement actions executed and outcomes assessed by Q3.
P4.26.G1 ★ | Achieve CFAI accreditation candidate status by formalizing the Accreditation SOG, implementing compliant processes across all applicable categories, gathering documented proof of compliance, and submitting the CFAI candidate application by Q4. | P4.27.G1 | Advance CFAI accreditation progress by completing all assigned tasks, incorporating 11th edition manual requirements, gathering ongoing proof of compliance across all categories, and reaching the next defined accreditation milestone by Q4.
P4.27.G1 ★ | Advance CFAI accreditation progress by completing all assigned tasks, incorporating 11th edition manual requirements, gathering ongoing proof of compliance across all categories, and reaching the next defined accreditation milestone by Q4. | P4.29.G1 | Establish a Historical and Archive Committee with a formal mandate, recruited membership, and completed initial inventory of historical items by Q2, and implement agency performance standards with a documented compliance tracking and evaluation process by Q4.
P4.28.G2 ★ | Develop a Mobile Integrated Healthcare operational framework including target population analysis, partner identification, performance measures, referral pathways, and a financial and staffing feasibility evaluation, and present an MIH implementation recommendation to command staff by Q4. | P4.29.G2 | Implement the Mobile Integrated Healthcare program by establishing formal healthcare partnerships, completing all policy and documentation frameworks, launching a pilot serving identified high-utilizer or at-risk populations by Q4, and initiating quarterly outcomes tracking.
P4.28.G3 ★ | Evaluate the demand, financial viability, staffing requirements, and operational feasibility of a minimum of two advanced EMS service models, and present a prioritized implementation strategy with go/no-go recommendations to executive leadership by Q4. | P4.29.G3 | Implement a minimum of one advanced EMS service model based on FY28 feasibility findings with a documented operational framework, trained personnel, and structured outcomes tracking, and deliver a first-year performance report to command staff by Q4.

## Changelog
CHANGELOG
Timestamp | Type | Goal | Detail
2026-06-14T11:54:26.362Z | status | P4.26.G1 | Implement processes and move toward best practice alignment. not-started → complete
2026-06-14T11:54:25.872Z | status | P4.26.G1 | Gather proof of compliance. not-started → complete
2026-06-14T11:54:24.641Z | status | P4.26.G1 | Achieve CFAI applicant status. not-started → complete
2026-06-14T11:54:21.996Z | status | P3.26.G2 | Formalize Senior Public Education program. not-started → complete
2026-06-14T11:54:21.652Z | status | P3.26.G2 | Formalize Elementary School CRR Education program. not-started → complete
2026-06-14T11:54:20.987Z | status | P3.26.G2 | Establish programs based on greatest identified need from da not-started → complete
2026-06-14T11:54:09.487Z | status | P3.26.G1 | Organize data and rank by importance, financial impact, and not-started → complete
2026-06-14T11:54:09.076Z | status | P3.26.G1 | Access and compile data from ImageTrend, police reporting, G not-started → complete
2026-06-14T11:54:05.576Z | status | P2.26.G3 | Develop clear job descriptions and roles for specific traini not-started → complete
2026-06-14T11:54:05.057Z | status | P2.26.G3 | Assess current staffing and workload distribution. not-started → complete
2026-06-14T11:54:00.882Z | status | P2.26.G2 | Relaunch revised ODP with defined enrollment criteria and de complete → not-started
2026-06-14T11:53:56.405Z | status | P2.26.G2 | Relaunch revised ODP with defined enrollment criteria and de not-started → complete
2026-06-14T11:53:54.938Z | status | P2.26.G2 | Collect and review feedback forms. not-started → complete
2026-06-14T11:53:52.167Z | status | P2.26.G2 | Develop education program. not-started → complete
2026-06-14T11:53:05.361Z | status | P1.26.G1 | Re-evaluate plans following drill and identify additional ne not-started → complete
2026-06-14T11:53:04.624Z | status | P1.26.G1 | Plan and conduct a large-scale drill including active shoote not-started → complete
2026-06-13T17:14:02.045Z | edit_goal | P1.27.G1 | Edited: year=FY27, domain=Incident Preparedness, predecessor=none
2026-06-12T21:43:01.168Z | edit_pillar |  | P4 â†’ P4: Professional Standards and Service Excellence
2026-06-12T21:42:54.225Z | edit_pillar |  | P3 â†’ P3: Community Risk Reduction and Public Education
2026-06-12T21:33:57.627Z | status | P2.26.G1 | Identify personnel leaving within the next five years. not-started → complete
2026-06-12T21:33:56.329Z | status | P2.26.G2 | Update and revise job descriptions. not-started → complete
2026-06-12T21:33:48.410Z | status | P1.26.G1 | Develop a response plan for each identified threat. not-started → complete
2026-06-12T21:33:47.803Z | status | P1.26.G1 | Identify major incident threat types across all hazard types not-started → complete