## Cover
NORTH PORT FIRE RESCUE
Strategic Plan · FY2026 – FY2029
MISSION
Provide exceptional public safety services in a safe, compassionate, and professional manner.
VISION
To be confirmed by command staff
VALUES
Trust · Family · Dedication · Compassion
STRATEGIC PILLARS
P1 | Operational Readiness — Steward: Scott Lane (0/30 tasks, 0%)
P2 | Workforce Development and Succession — Steward: Adam Inlow (2/34 tasks, 6%)
P3 | Personnel Health, Wellness, and Culture — Steward: Scott Lane (0/28 tasks, 0%)
P4 | Community Risk Reduction and Engagement — Steward: Peter Marietti (0/39 tasks, 0%)
P5 | Clinical Excellence and EMS Innovation — Steward: Nick Satterly (3/26 tasks, 12%)
P6 | Infrastructure, Technology, and Fiscal Stewardship — Steward: Nick Herlihy (2/29 tasks, 7%)
Generated June 09, 2026 · Initial migration — IDs updated to P#.YY.G# format

## Summary
STRATEGIC PLAN SUMMARY
Pillar | Name | Steward | Goals | Tasks | Done | Complete %
P1 | Operational Readiness | Scott Lane | 6 | 30 | 0 | 0%
P2 | Workforce Development and Succession | Adam Inlow | 7 | 34 | 2 | 5.882%
P3 | Personnel Health, Wellness, and Culture | Scott Lane | 6 | 28 | 0 | 0%
P4 | Community Risk Reduction and Engagement | Peter Marietti | 9 | 39 | 0 | 0%
P5 | Clinical Excellence and EMS Innovation | Nick Satterly | 7 | 26 | 3 | 11.54%
P6 | Infrastructure, Technology, and Fiscal Stewardship | Nick Herlihy | 7 | 29 | 2 | 6.897%
TOTAL |  |  |  | 186 | 7 | 3.763%

## By Year
GOALS BY FISCAL YEAR
FY26
Goal ID | Pillar | Goal Statement | Owner | Status | Success Metric
P1.26.G1 | Operational Readin | Evaluate the current deployment model against 36 months of incident data to identify gaps in response capability, unit utilization, and geographic coverage. | TBD | Not Started | A completed deployment evaluation report reviewed and accepted by command staff, with gaps and recommendations documented.
P1.26.G2 | Operational Readin | Develop and implement a sustainable two-set PPE management program establishing reserve inventory standards, lifecycle replacement schedules, and long-term funding projections. | TBD | Not Started | A documented PPE lifecycle replacement model with annual funding projections adopted and integrated into the budget process.
P2.26.G1 | Workforce Developm | Identify all member development gaps, career pathways, and critical functions across the department to establish the foundation for succession and development planning. | TBD | Not Started | A completed department-wide gap analysis report documenting all job functions, development needs, career pathways, and identified gaps, accepted by command staff.
P2.26.G2 | Workforce Developm | Develop and implement a formal recruitment and selection process aligned to operational needs, including targeted outreach, standardized interview criteria, a scoring system, and a recruitment committee. | TBD | In Progress | A fully documented recruitment and selection process in place, with a recruitment committee established and at least one full hiring cycle completed under the new process.
P3.26.G1 | Personnel Health, | Identify and assess department health and wellness needs through workforce survey, industry comparison, and facility evaluation, and report findings to inform program development. | Scott Lane | Not Started | A completed health and wellness needs assessment report with findings and program recommendations accepted by command staff.
P3.26.G2 | Personnel Health, | Develop and implement programs addressing behavioral health, PTSD support, cancer prevention, nutrition, fitness, and chaplain services, based on the findings from P3.26.G1. | Scott Lane | Not Started | At least three health and wellness programs formally adopted, funded, and operational with documented participation metrics.
P3.26.G3 | Personnel Health, | Enhance mental health and compassion communication training for all operational personnel, covering death notification, de-escalation, crisis intervention, and a formal qualifying incident support protocol. | TBD | Not Started | 100% of operational personnel complete the training, and a qualifying incident support protocol is adopted and in place.
P4.26.G1 | Community Risk Red | Gather and organize incident and community risk data across five task areas to establish a baseline for all CRR program development. | TBD | In Progress | A completed, organized community risk dataset covering all five task areas, ranked by priority and available to the CRR team for analysis.
P4.26.G2 | Community Risk Red | Expand the car seat technician program by increasing certified personnel, improving scheduling and community availability, and building program succession to ensure long-term sustainability. | Dave Ingalls | Not Started | Increased number of certified technicians, documented improvement in scheduling availability, and a succession plan in place for the program.
P5.26.G1 | Clinical Excellenc | Earn the AHA Mission Lifeline Gold Rating through consistent monitoring of cardiac care performance metrics, quarterly data reporting, and timely submission of all required measures. | Nick Satterly | In Progress | AHA Mission Lifeline Gold Rating achieved and maintained through the fiscal year.
P5.26.G2 | Clinical Excellenc | Establish hospital clinical rotation opportunities for paramedics covering airway management, RSI exposure, surgical airway familiarity, and critical care observation. | Dave Ingalls | Not Started | At least one hospital partnership formalized with a documented rotation program and baseline participation numbers recorded in the first year.
P6.26.G1 | Infrastructure, Te | Modernize apparatus and fleet maintenance tracking by implementing a system that accurately captures complaint dates, repair timelines, return-to-service data, and key performance indicators for all vehicles. | Terry Mccloud | Not Started | A functional fleet tracking system capturing all defined KPIs, with a baseline year of data collected and an initial cost and downtime analysis completed.
P6.26.G2 | Infrastructure, Te | Obtain and maintain ISO 1 rating and advance the department's CFAI accreditation through coordinated stakeholder engagement, infrastructure improvement, and documentation compliance. | Nick Herlihy | In Progress | ISO 1 rating maintained and CFAI accreditation status advanced with all required documentation submitted on schedule.
FY27
Goal ID | Pillar | Goal Statement | Owner | Status | Success Metric
P1.27.G1 | Operational Readin | Develop and implement a major incident response planning program covering all identified threat types within NPFR's response model, aligned to deployment gaps identified in P1.26.G1. | TBD | Not Started | Documented response plans for all identified major incident threat types, with at least one plan validated through a full-scale or tabletop exercise.
P1.27.G2 | Operational Readin | Enhance hazardous materials response capability by expanding technician-level certification, developing a target hazard pre-plan library, and establishing a regular HOT training cadence. | TBD | Not Started | Increased number of Hazmat Technician-certified personnel, a completed target hazard pre-plan library, and a documented annual training schedule.
P1.27.G3 | Operational Readin | Establish three strategically located logistics resource hubs using locker technology to improve access to EMS supplies, reserve equipment, and operational resources while reducing replenishment demands. | TBD | Not Started | Three logistics resource hubs operational with documented SOGs, trained personnel, and a baseline effectiveness evaluation completed within the first year of operation.
P2.27.G1 | Workforce Developm | Develop and implement career development pathways and supporting policies for all department positions, based on the gap analysis findings from P2.26.G1. | TBD | In Progress | Documented career development pathways for all positions published and distributed department-wide, with supporting policies adopted.
P2.27.G2 | Workforce Developm | Develop and implement a department-wide succession plan covering all positions, built through multi-level organizational input and aligned to the career pathways established in P2.27.G1. | TBD | In Progress | A completed, adopted succession plan document covering all identified critical positions, reviewed by command staff and integrated into the ODP.
P2.27.G3 | Workforce Developm | Create a structured administrative development program that provides interested line personnel with meaningful exposure to departmental administrative functions, building internal bench strength before vacancies arise. | TBD | Not Started | Program launched with documented structure, at least one cohort of participants completed, and a formal evaluation of outcomes conducted.
P3.27.G1 | Personnel Health, | Develop and implement a department-wide internal communication program that improves the consistent flow of information between administrative and line personnel across all shifts and stations. | TBD | Not Started | A formal internal communication program launched with at least two active channels, a documented station visit schedule, and a measured improvement in member awareness.
P3.27.G2 | Personnel Health, | Establish and implement a station facilities service and replacement schedule for all high-use station equipment, covering both Facilities-managed and department-managed items. | Kyle Dent | Not Started | A documented service and replacement schedule in place for all identified station equipment categories, with a corresponding budget line item established.
P4.27.G1 | Community Risk Red | Evaluate and rank the community risk data gathered in P4.26.G1 to identify the highest-priority program areas and determine staffing, resource, and policy requirements for program development. | TBD | Not Started | A prioritized CRR program development plan accepted by command staff, with identified staffing requirements and at least two new programs approved for development.
P4.27.G2 | Community Risk Red | Develop a fire explorer and cadet pathway program in partnership with local high schools that creates a structured pipeline for future firefighter recruitment. | Jay Sousa | Not Started | A formal explorer or cadet program established with at least one partner high school, annual touchpoint events scheduled, and a baseline recruitment outcome metric defined.
P4.27.G3 | Community Risk Red | Develop and implement a one-week youth summer camp in partnership with NPPD and Parks and Recreation that promotes safety awareness, community engagement, and positive interactions with NPFR personnel. | Michael Tackman | Not Started | First summer camp session conducted with documented participation numbers, partner agreements in place, and a post-event evaluation completed.
P4.27.G4 | Community Risk Red | Establish a school zone fire department presence program at the start of each school year and return from long seasonal breaks to reinforce traffic safety awareness at high-risk crosswalks. | Kyle Dent | Not Started | Program deployed at all identified high-risk school zone crosswalks for at least one start-of-year event, with NPPD coordination documented.
P5.27.G1 | Clinical Excellenc | Develop and implement major incident response plans for EMS-specific threat types, including mass casualty events, ensuring protocols align with current best practices. | Nick Satterly | In Progress | Documented EMS major incident response plans for all identified threat types, with at least one plan validated through an exercise.
P5.27.G2 | Clinical Excellenc | Develop and implement a community paramedicine program that identifies high-utilization populations, establishes governing policies and practices, and launches a pilot program. | Matt Petitt | Not Started | Community paramedicine program operational with documented policies, a defined patient population, and at least six months of utilization and outcome data collected.
P6.27.G1 | Infrastructure, Te | Analyze fleet maintenance cost and effectiveness data collected in P6.26.G1 to identify outsourcing opportunities, evaluate in-house EVT feasibility, and develop long-term cost reduction strategies. | Terry Mccloud | Not Started | A completed fleet cost and effectiveness analysis with specific recommendations on outsourcing and EVT feasibility presented to command staff and city leadership.
P6.27.G2 | Infrastructure, Te | Evaluate and improve interoperability between scheduling and payroll platforms, specifically CrewSense and ExecuTime, to reduce administrative correction workload and improve payroll accuracy. | Dave Ingalls | Not Started | A documented reduction in payroll correction workload and measurable improvement in payroll accuracy following implementation.
P6.27.G3 | Infrastructure, Te | Migrate departmental records to a centralized, access-controlled digital library that meets retention requirements, with proper file mapping, access controls, and disposition of records that have met retention. | Anna Duffey | Not Started | All active departmental records migrated to the centralized library with a documented file map, access control structure, and a completed disposition log.
P6.27.G4 | Infrastructure, Te | Create a Historical and Archive Committee to identify, catalogue, and maintain records and other items of historical significance to the department. | Anna Duffey | Not Started | Committee established with a formal mandate and at least one complete inventory of historical items with documented storage and handling procedures.
FY28
Goal ID | Pillar | Goal Statement | Owner | Status | Success Metric
P1.28.G1 | Operational Readin | Develop and implement a logistics operational resiliency program that eliminates single-point dependencies through knowledge management, cross-training, and continuity planning across all critical logistics functions. | TBD | Not Started | Continuity guides completed for all identified single-point-of-dependency functions, with at least one annual exercise conducted and documented.
P2.28.G1 | Workforce Developm | Achieve and maintain 90% or greater professional credentialing of all applicable positions aligned with CFAI credentialing categories, integrated into the succession plan and Officer Development Program. | Nick Herlihy | Not Started | 90% or greater of applicable positions credentialed within CFAI categories, with individual completion plans documented for all remaining positions.
P3.28.G1 | Personnel Health, | Evaluate the adequacy of current educational assistance funding relative to current tuition costs and internal career advancement requirements, and present findings and recommendations to city leadership. | TBD | Not Started | A completed analysis presented to city leadership with a formal funding recommendation, and a documented outcome from that presentation.
P4.28.G1 | Community Risk Red | Develop and launch a comprehensive community risk reduction program with targeted interventions in fire prevention, drowning prevention, fall prevention, CPR training, and severe weather preparedness. | Jay Sousa | Not Started | At least three formal CRR programs launched with documented reach metrics including number of participants, events, and geographic coverage.
P4.28.G2 | Community Risk Red | Establish a community outreach team of 10 to 15 trained firefighters who can support public education presentations and CRR events across the community. | Jay Sousa | Not Started | A functioning community outreach team of at least 10 trained members with documented event participation in the first year of operation.
P5.28.G1 | Clinical Excellenc | Analyze incident data from community paramedicine operations to identify populations where a mobile integrated health program would reduce resource utilization and improve outcomes, and establish the program framework. | Nick Satterly | Not Started | MIH program framework adopted and operational with trained providers, at least one formal partner agreement in place, and baseline utilization data being tracked.
P5.28.G2 | Clinical Excellenc | Evaluate the feasibility, return on investment, and strategic placement of a specialty care transport unit within the current response model, and establish response guidelines if the program moves forward. | Nick Satterly | Not Started | A completed feasibility analysis and ROI assessment presented to command staff with a documented go or no-go recommendation.
P5.28.G3 | Clinical Excellenc | Strengthen relationships with local hospitals and healthcare systems to support joint education programs, MIH referral pathways, and collaborative community health initiatives. | Jay Sousa | Not Started | At least two formal hospital partnerships documented with defined collaboration scope, and at least one joint community education event conducted.
FY29
Goal ID | Pillar | Goal Statement | Owner | Status | Success Metric
P2.29.G1 | Workforce Developm | Pursue regional recognition as a fire training resource by establishing institutional partnerships, gaining applicable accreditation, and hosting accredited training offerings for external agencies. | TBD | Not Started | Regional accreditation obtained, at least two accredited training sessions hosted, and a 50% increase in collaborative training events with external agencies documented.
P4.29.G1 | Community Risk Red | Expand upon the three most successful CRR programs based on effectiveness data, improve weaker programs, and establish a state-level presence advocating for residential fire sprinkler requirements. | TBD | Not Started | Documented expansion of three top-performing programs, improvement plans implemented for weaker programs, and at least one state-level engagement on residential sprinkler advocacy completed.
P6.29.G1 | Infrastructure, Te | Establish and maintain a formal periodic policy review process within PowerDMS ensuring 95% on-time completion, zero overdue reviews, and regulatory compliance across all departmental policies. | Tammie Wichers | Not Started | Zero overdue policy reviews in PowerDMS, 95% or higher on-time completion rate sustained, and all policies assigned to an owner and subject matter expert.

## P1 Operational Readines
P1 — Operational Readiness
Steward: Scott Lane
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P1.26.G1 ★ | FY26 | Not Started | — | Evaluate the current deployment model against 36 months of incident data to identify gaps in response capability, unit utilization, and geographic coverage. | TBD | T1 | Gather incident data from the last 36 months and separate by incident type. | Not Started | A completed deployment evaluation report reviewed and accepted by command staff, with gaps and recommendations documented.
[6 empty] | T2 | Review and rank incident types by frequency, severity, and resource demand. | Not Started
[6 empty] | T3 | Evaluate the current deployment model against identified incident patterns. | Not Started
[6 empty] | T4 | Identify gaps in coverage, staffing configuration, or unit positioning. | Not Started
[6 empty] | T5 | Produce a deployment evaluation report with findings and recommendations. | Not Started
P1.26.G2 | FY26 | Not Started | — | Develop and implement a sustainable two-set PPE management program establishing reserve inventory standards, lifecycle replacement schedules, and long-term funding projections. | TBD | T1 | Conduct a comprehensive assessment of current PPE inventory including primary, secondary, reserve, and specialty sizing needs. | Not Started | A documented PPE lifecycle replacement model with annual funding projections adopted and integrated into the budget process.
[6 empty] | T2 | Develop minimum reserve PPE inventory standards to support recruit academies, new hires, damaged gear replacement, and emergency replacements. | Not Started
[6 empty] | T3 | Create a long-term PPE lifecycle replacement model accounting for the recent bulk purchase, projected retirements, and department growth. | Not Started
[6 empty] | T4 | Develop procedures within Honeywell First to monitor PPE assignment, serviceability, inspection compliance, and replacement forecasting. | Not Started
[6 empty] | T5 | Implement a sustainable PPE readiness program with annual review processes, reserve inventory targets, and replacement funding recommendations. | Not Started
FY27
P1.27.G1 | FY27 | Not Started | P1.26.G1 | Develop and implement a major incident response planning program covering all identified threat types within NPFR's response model, aligned to deployment gaps identified in P1.26.G1. | TBD | T1 | Identify major incident threat types from the deployment evaluation findings. | Not Started | Documented response plans for all identified major incident threat types, with at least one plan validated through a full-scale or tabletop exercise.
[6 empty] | T2 | Review current response plans for alignment with identified threats and deployment model. | Not Started
[6 empty] | T3 | Develop a plan for each identified threat type including resource, staffing, and training requirements. | Not Started
[6 empty] | T4 | Plan and conduct a large-scale drill to test at least one major incident plan. | Not Started
[6 empty] | T5 | Establish a regular review and update cycle for all major incident plans. | Not Started
P1.27.G2 | FY27 | Not Started | — | Enhance hazardous materials response capability by expanding technician-level certification, developing a target hazard pre-plan library, and establishing a regular HOT training cadence. | TBD | T1 | Increase the number of personnel certified to the Hazardous Materials Technician level to serve as future FTOs. | Not Started | Increased number of Hazmat Technician-certified personnel, a completed target hazard pre-plan library, and a documented annual training schedule.
[6 empty] | T2 | Create a target hazard list for the city and develop incident response pre-plans for each site. | Not Started
[6 empty] | T3 | Establish annual or bi-annual HOT training and tabletop exercises led by Hazmat-certified FTOs. | Not Started
[6 empty] | T4 | Evaluate additional equipment needs to support safe response and mitigation within NPFR's scope. | Not Started
[6 empty] | T5 | Review and update any relevant policies or protocols to reflect capability changes. | Not Started
P1.27.G3 ★ | FY27 | Not Started | P1.26.G1 | Establish three strategically located logistics resource hubs using locker technology to improve access to EMS supplies, reserve equipment, and operational resources while reducing replenishment demands. | TBD | T1 | Conduct a needs assessment and geographic analysis using call volume and resource utilization data from the deployment evaluation to identify three hub stations. | Not Started | Three logistics resource hubs operational with documented SOGs, trained personnel, and a baseline effectiveness evaluation completed within the first year of operation.
[6 empty] | T2 | Develop a logistics resource hub program defining inventory categories, stocking levels, replenishment procedures, and accountability measures. | Not Started
[6 empty] | T3 | Purchase and install locker systems at designated hub locations and configure inventory management and access control processes. | Not Started
[6 empty] | T4 | Develop and implement SOGs and training for hub access, inventory accountability, and equipment tracking. | Not Started
[6 empty] | T5 | Evaluate program effectiveness by measuring replenishment frequency, labor hours, inventory availability, and user feedback. | Not Started
FY28
P1.28.G1 | FY28 | Not Started | P1.27.G3 | Develop and implement a logistics operational resiliency program that eliminates single-point dependencies through knowledge management, cross-training, and continuity planning across all critical logistics functions. | TBD | T1 | Identify critical logistics functions, systems, and responsibilities currently dependent on a single employee or position. | Not Started | Continuity guides completed for all identified single-point-of-dependency functions, with at least one annual exercise conducted and documented.
[6 empty] | T2 | Develop position-specific continuity guides and SOPs for all critical logistics functions. | Not Started
[6 empty] | T3 | Establish a cross-training program providing secondary personnel with foundational knowledge of critical logistics responsibilities. | Not Started
[6 empty] | T4 | Develop a logistics division continuity plan identifying backup personnel, vendor contacts, and operating procedures for extended absences. | Not Started
[6 empty] | T5 | Conduct annual continuity exercises to validate documentation and assess cross-training effectiveness. | Not Started

## P2 Workforce Developmen
P2 — Workforce Development and Succession
Steward: Adam Inlow
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P2.26.G1 ★ | FY26 | Not Started | — | Identify all member development gaps, career pathways, and critical functions across the department to establish the foundation for succession and development planning. | TBD | T1 | Identify all job functions within the department. | Not Started | A completed department-wide gap analysis report documenting all job functions, development needs, career pathways, and identified gaps, accepted by command staff.
[6 empty] | T2 | Identify training and development needs associated with each function. | Not Started
[6 empty] | T3 | Identify all career pathways and critical succession roles. | Not Started
[6 empty] | T4 | Identify gaps between current capability and future need. | Not Started
[6 empty] | T5 | Produce a gap analysis report with findings and prioritized recommendations. | Not Started
P2.26.G2 | FY26 | In Progress | — | Develop and implement a formal recruitment and selection process aligned to operational needs, including targeted outreach, standardized interview criteria, a scoring system, and a recruitment committee. | TBD | T1 | Evaluate the prior fiscal year's applicant pool for quality, source, and diversity. | Complete | A fully documented recruitment and selection process in place, with a recruitment committee established and at least one full hiring cycle completed under the new process.
[6 empty] | T2 | Partner with local technical schools and educational institutions to build a recruitment pipeline. | Complete
[6 empty] | T3 | Develop an online recruitment portal and outreach materials including a QR code-based campaign. | In Progress
[6 empty] | T4 | Develop standardized interview questions, a documented scoring system, and establish a recruitment committee. | In Progress
[6 empty] | T5 | Evaluate the selection process against new employee performance at the 12-month review. | Not Started
FY27
P2.27.G1 ★ | FY27 | In Progress | P2.26.G1 | Develop and implement career development pathways and supporting policies for all department positions, based on the gap analysis findings from P2.26.G1. | TBD | T1 | Develop pathways for member development covering all identified positions and career progressions. | Not Started | Documented career development pathways for all positions published and distributed department-wide, with supporting policies adopted.
[6 empty] | T2 | Develop any needed policies or procedures governing pathway participation and progression. | Not Started
[6 empty] | T3 | Establish roles, responsibilities, and division oversight for the training function. | In Progress
[6 empty] | T4 | Present the development pathways to all department members. | Not Started
[6 empty] | T5 | Implement the pathways and establish a continuous evaluation process for workload, roles, and growth. | Not Started
P2.27.G2 ★ | FY27 | In Progress | P2.27.G1 | Develop and implement a department-wide succession plan covering all positions, built through multi-level organizational input and aligned to the career pathways established in P2.27.G1. | TBD | T1 | Identify personnel projected to leave within the next five years. | In Progress | A completed, adopted succession plan document covering all identified critical positions, reviewed by command staff and integrated into the ODP.
[6 empty] | T2 | Map specific career pathways for all succession-critical positions. | Not Started
[6 empty] | T3 | Develop the succession plan document using input from various levels of the organization. | In Progress
[6 empty] | T4 | Review the plan and incorporate feedback before finalizing. | Not Started
[6 empty] | T5 | Implement the succession plan and integrate it into the Officer Development Program. | Not Started
P2.27.G3 | FY27 | Not Started | P2.27.G1 | Create a structured administrative development program that provides interested line personnel with meaningful exposure to departmental administrative functions, building internal bench strength before vacancies arise. | TBD | T1 | Identify administrative and specialty roles with historically difficult transitions or knowledge gaps. | Not Started | Program launched with documented structure, at least one cohort of participants completed, and a formal evaluation of outcomes conducted.
[6 empty] | T2 | Develop a structured rotation or shadow program giving line personnel access to administrative functions. | Not Started
[6 empty] | T3 | Build internal succession planning components into the program tied to the career pathways from P2.27.G1. | Not Started
[6 empty] | T4 | Create evaluation criteria to measure participant development and program effectiveness. | Not Started
[6 empty] | T5 | Encourage personnel to explore leadership paths before promotional timelines through active program promotion. | Not Started
FY28
P2.28.G1 | FY28 | Not Started | P2.27.G2 | Achieve and maintain 90% or greater professional credentialing of all applicable positions aligned with CFAI credentialing categories, integrated into the succession plan and Officer Development Program. | Nick Herlihy | T1 | Meet with all staff who have an associated CFAI credential category to assess current credentialing status. | Not Started | 90% or greater of applicable positions credentialed within CFAI categories, with individual completion plans documented for all remaining positions.
[6 empty] | T2 | Integrate credentialing requirements into the department succession plan document. | Not Started
[6 empty] | T3 | Develop an individual completion plan for all applicable staff members. | Not Started
[6 empty] | T4 | Incorporate credentialing milestones into the NPFR Officer Development Program. | Not Started
FY29
P2.29.G1 | FY29 | Not Started | P2.27.G1 | Pursue regional recognition as a fire training resource by establishing institutional partnerships, gaining applicable accreditation, and hosting accredited training offerings for external agencies. | TBD | T1 | Establish and strengthen relationships with regional educational institutions and decision makers. | Not Started | Regional accreditation obtained, at least two accredited training sessions hosted, and a 50% increase in collaborative training events with external agencies documented.
[6 empty] | T2 | Establish or maintain articulation agreements with local institutions. | Not Started
[6 empty] | T3 | Reduce reliance on external training by formalizing shared resource agreements for training facilities. | Not Started
[6 empty] | T4 | Gain regional accreditation and host at least two accredited training sessions within the fiscal year. | Not Started
[6 empty] | T5 | Increase collaborative training events by 50% with external agencies through joint training agreements. | Not Started

## P3 Personnel Health, We
P3 — Personnel Health, Wellness, and Culture
Steward: Scott Lane
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P3.26.G1 ★ | FY26 | Not Started | — | Identify and assess department health and wellness needs through workforce survey, industry comparison, and facility evaluation, and report findings to inform program development. | Scott Lane | T1 | Review all current relevant health and wellness policies. | Not Started | A completed health and wellness needs assessment report with findings and program recommendations accepted by command staff.
[6 empty] | T2 | Conduct a department-wide workforce survey on health, fitness, and wellness needs. | Not Started
[6 empty] | T3 | Compare survey results to industry standards and benchmarks. | Not Started
[6 empty] | T4 | Evaluate current fitness facilities at all stations. | Not Started
[6 empty] | T5 | Compile and report findings to command staff. | Not Started
P3.26.G2 | FY26 | Not Started | P3.26.G1 | Develop and implement programs addressing behavioral health, PTSD support, cancer prevention, nutrition, fitness, and chaplain services, based on the findings from P3.26.G1. | Scott Lane | T1 | Research programs in the following areas: firefighter cancer prevention, fitness, behavioral health, nutrition, and department chaplain. | Not Started | At least three health and wellness programs formally adopted, funded, and operational with documented participation metrics.
[6 empty] | T2 | Develop annual workforce task evaluations and an annual fitness assessment designed around position tasks. | Not Started
[6 empty] | T3 | Determine which programs align with the department's vision for health and wellness based on assessment findings. | Not Started
[6 empty] | T4 | Secure funding for adopted programs through budget requests and grant opportunities. | Not Started
[6 empty] | T5 | Implement adopted programs and establish review processes for ongoing effectiveness. | Not Started
P3.26.G3 | FY26 | Not Started | — | Enhance mental health and compassion communication training for all operational personnel, covering death notification, de-escalation, crisis intervention, and a formal qualifying incident support protocol. | TBD | T1 | Identify current training gaps in death notification, de-escalation, and crisis communication. | Not Started | 100% of operational personnel complete the training, and a qualifying incident support protocol is adopted and in place.
[6 empty] | T2 | Develop or procure specialized training curriculum covering all identified topic areas. | Not Started
[6 empty] | T3 | Deliver training to all operational personnel within the fiscal year. | Not Started
[6 empty] | T4 | Establish criteria for qualifying PTSD-related incidents and create a protocol for members requesting support time. | Not Started
[6 empty] | T5 | Implement the support protocol and follow up with data to assess effectiveness. | Not Started
FY27
P3.27.G1 | FY27 | Not Started | — | Develop and implement a department-wide internal communication program that improves the consistent flow of information between administrative and line personnel across all shifts and stations. | TBD | T1 | Identify current communication gaps and avenues for contact between officer and line personnel. | Not Started | A formal internal communication program launched with at least two active channels, a documented station visit schedule, and a measured improvement in member awareness.
[6 empty] | T2 | Develop a rotating schedule for administrative officers to visit each station throughout the year. | Not Started
[6 empty] | T3 | Explore creation of a regular department newsletter containing updates, training highlights, apparatus news, and member recognition. | Not Started
[6 empty] | T4 | Explore digital and social media platforms for short-form training and informational content. | Not Started
[6 empty] | T5 | Identify budget requirements for platforms and content development. | Not Started
P3.27.G2 | FY27 | Not Started | — | Establish and implement a station facilities service and replacement schedule for all high-use station equipment, covering both Facilities-managed and department-managed items. | Kyle Dent | T1 | Review and categorize items serviced by Facilities and items serviced directly by the department. | Not Started | A documented service and replacement schedule in place for all identified station equipment categories, with a corresponding budget line item established.
[6 empty] | T2 | Explore service contracts with vendors and review manufacturer-recommended service and replacement schedules. | Not Started
[6 empty] | T3 | Create a tracking and monitoring system to prompt timely service requests. | Not Started
[6 empty] | T4 | Create a budget item reflecting recurring service and replacement costs. | Not Started
FY28
P3.28.G1 | FY28 | Not Started | — | Evaluate the adequacy of current educational assistance funding relative to current tuition costs and internal career advancement requirements, and present findings and recommendations to city leadership. | TBD | T1 | Identify the current cost of college courses relative to prior years and collect educational requirements for internal upward movement. | Not Started | A completed analysis presented to city leadership with a formal funding recommendation, and a documented outcome from that presentation.
[6 empty] | T2 | Establish criteria an employee must meet to qualify for increased levels of educational assistance. | Not Started
[6 empty] | T3 | Compare current and historical data to validate the need for funding increases. | Not Started
[6 empty] | T4 | Present findings and a funding recommendation to city leadership. | Not Started

## P4 Community Risk Reduc
P4 — Community Risk Reduction and Engagement
Steward: Peter Marietti
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P4.26.G1 ★ | FY26 | In Progress | — | Gather and organize incident and community risk data across five task areas to establish a baseline for all CRR program development. | TBD | T1 | Pull and organize data from ImageTrend covering incident types and outcomes. | In Progress | A completed, organized community risk dataset covering all five task areas, ranked by priority and available to the CRR team for analysis.
[6 empty] | T2 | Integrate police reporting data for relevant risk categories. | In Progress
[6 empty] | T3 | Pull and organize GIS-based risk and demographic data. | In Progress
[6 empty] | T4 | Integrate Mobile Eyes and regional data sources. | In Progress
[6 empty] | T5 | Compile all data into a single organized dataset ranked by incident frequency and community impact. | Not Started
P4.26.G2 | FY26 | Not Started | — | Expand the car seat technician program by increasing certified personnel, improving scheduling and community availability, and building program succession to ensure long-term sustainability. | Dave Ingalls | T1 | Identify current certified technicians and assess gaps in coverage and availability. | Not Started | Increased number of certified technicians, documented improvement in scheduling availability, and a succession plan in place for the program.
[6 empty] | T2 | Increase the number of certified Child Passenger Safety Technicians within the department. | Not Started
[6 empty] | T3 | Improve scheduling and availability for community events and inspection appointments. | Not Started
[6 empty] | T4 | Create a succession plan so the program remains sustainable as personnel turn over. | Not Started
FY27
P4.27.G1 ★ | FY27 | Not Started | P4.26.G1 | Evaluate and rank the community risk data gathered in P4.26.G1 to identify the highest-priority program areas and determine staffing, resource, and policy requirements for program development. | TBD | T1 | Organize and rank collected data by community impact, incident frequency, and prevention potential. | Not Started | A prioritized CRR program development plan accepted by command staff, with identified staffing requirements and at least two new programs approved for development.
[6 empty] | T2 | Evaluate the financial and organizational impact of addressing each identified risk area. | Not Started
[6 empty] | T3 | Establish programs based on greatest identified need. | Not Started
[6 empty] | T4 | Identify staffing requirements for program implementation including a second dedicated CRR staff position. | Not Started
[6 empty] | T5 | Formalize SOGs for the Fire Marshal function to support CRR program delivery. | Not Started
P4.27.G2 | FY27 | Not Started | — | Develop a fire explorer and cadet pathway program in partnership with local high schools that creates a structured pipeline for future firefighter recruitment. | Jay Sousa | T1 | Develop a Fire Explorer and cadet pathway with local high schools. | Not Started | A formal explorer or cadet program established with at least one partner high school, annual touchpoint events scheduled, and a baseline recruitment outcome metric defined.
[6 empty] | T2 | Create annual station visits and career days for students. | Not Started
[6 empty] | T3 | Identify whether the current cadet program produces measurable recruitment outcomes through school completion and job placement tracking. | Not Started
P4.27.G3 | FY27 | Not Started | — | Develop and implement a one-week youth summer camp in partnership with NPPD and Parks and Recreation that promotes safety awareness, community engagement, and positive interactions with NPFR personnel. | Michael Tackman | T1 | Research similar youth camp models including the Charlotte County Sheriff's Office Junior Law Academy. | Not Started | First summer camp session conducted with documented participation numbers, partner agreements in place, and a post-event evaluation completed.
[6 empty] | T2 | Identify target age group, staffing needs, facilities, transportation, and risk management requirements. | Not Started
[6 empty] | T3 | Meet with NPPD and Parks and Recreation to discuss partnership and shared staffing. | Not Started
[6 empty] | T4 | Develop program curriculum to include safety education, apparatus tours, team activities, and community service. | Not Started
P4.27.G4 | FY27 | Not Started | — | Establish a school zone fire department presence program at the start of each school year and return from long seasonal breaks to reinforce traffic safety awareness at high-risk crosswalks. | Kyle Dent | T1 | Review traffic patterns and identify high-risk crosswalks associated with each school zone in the city. | Not Started | Program deployed at all identified high-risk school zone crosswalks for at least one start-of-year event, with NPPD coordination documented.
[6 empty] | T2 | Review sunrise patterns and lighting conditions at affected crosswalks for early morning bus stops. | Not Started
[6 empty] | T3 | Include NPPD in the analysis and coordinate joint deployment where appropriate. | Not Started
[6 empty] | T4 | Develop signage for crews to display at intersections reinforcing school zone speed awareness. | Not Started
[6 empty] | T5 | Review and align shift schedules to coincide with deployment windows. | Not Started
FY28
P4.28.G1 ★ | FY28 | Not Started | P4.27.G1 | Develop and launch a comprehensive community risk reduction program with targeted interventions in fire prevention, drowning prevention, fall prevention, CPR training, and severe weather preparedness. | Jay Sousa | T1 | Build out new program policies and content for the highest-priority risk areas identified in P4.27.G1. | Not Started | At least three formal CRR programs launched with documented reach metrics including number of participants, events, and geographic coverage.
[6 empty] | T2 | Formalize elementary school CRR education programming. | Not Started
[6 empty] | T3 | Formalize senior public education programming. | Not Started
[6 empty] | T4 | Target outreach to align with incident data by ensuring program deployment matches geographic and demographic risk concentrations. | Not Started
[6 empty] | T5 | Begin phased program rollout across all identified priority areas. | Not Started
P4.28.G2 | FY28 | Not Started | P4.28.G1 | Establish a community outreach team of 10 to 15 trained firefighters who can support public education presentations and CRR events across the community. | Jay Sousa | T1 | Train firefighters interested in public education roles. | Not Started | A functioning community outreach team of at least 10 trained members with documented event participation in the first year of operation.
[6 empty] | T2 | Create a roster of 10 to 15 members available to assist with presentations and events. | Not Started
[6 empty] | T3 | Analyze the internal and external impact of line personnel engaged in CRR activities. | Not Started
FY29
P4.29.G1 | FY29 | Not Started | P4.28.G1 | Expand upon the three most successful CRR programs based on effectiveness data, improve weaker programs, and establish a state-level presence advocating for residential fire sprinkler requirements. | TBD | T1 | Access effectiveness data from ImageTrend, CARES database, GIS, regional sources, and external surveys. | Not Started | Documented expansion of three top-performing programs, improvement plans implemented for weaker programs, and at least one state-level engagement on residential sprinkler advocacy completed.
[6 empty] | T2 | Compare current program data to baseline and identify programs with the strongest outcomes. | Not Started
[6 empty] | T3 | Expand upon proven strengths in the top three performing programs. | Not Started
[6 empty] | T4 | Identify and implement improvement plans for the three weakest programs. | Not Started
[6 empty] | T5 | Strategize and establish a state-level presence to promote residential fire sprinkler requirements. | Not Started

## P5 Clinical Excellence
P5 — Clinical Excellence and EMS Innovation
Steward: Nick Satterly
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P5.26.G1 | FY26 | In Progress | — | Earn the AHA Mission Lifeline Gold Rating through consistent monitoring of cardiac care performance metrics, quarterly data reporting, and timely submission of all required measures. | Nick Satterly | T1 | Monitor current and future cardiac care metrics on an ongoing basis. | In Progress | AHA Mission Lifeline Gold Rating achieved and maintained through the fiscal year.
[6 empty] | T2 | Ensure protocols continue to meet best practices. | Complete
[6 empty] | T3 | Conduct quarterly reporting of performance data. | In Progress
[6 empty] | T4 | Submit all required measures for Mission Lifeline Gold rating consideration. | In Progress
P5.26.G2 | FY26 | Not Started | — | Establish hospital clinical rotation opportunities for paramedics covering airway management, RSI exposure, surgical airway familiarity, and critical care observation. | Dave Ingalls | T1 | Partner with local hospitals to establish optional or scheduled clinical rotations. | Not Started | At least one hospital partnership formalized with a documented rotation program and baseline participation numbers recorded in the first year.
[6 empty] | T2 | Define rotation scope covering airway management, intubation, RSI exposure, surgical airway familiarity, and critical care observation. | Not Started
[6 empty] | T3 | Develop scheduling and documentation protocols for rotation participation. | Not Started
FY27
P5.27.G1 | FY27 | In Progress | — | Develop and implement major incident response plans for EMS-specific threat types, including mass casualty events, ensuring protocols align with current best practices. | Nick Satterly | T1 | Identify major incident threat types relevant to EMS operations. | Complete | Documented EMS major incident response plans for all identified threat types, with at least one plan validated through an exercise.
[6 empty] | T2 | Develop a plan for each identified EMS-specific threat type. | In Progress
[6 empty] | T3 | Plan and conduct a large-scale or tabletop exercise to validate at least one plan. | Complete
[6 empty] | T4 | Re-evaluate plans following the exercise and identify additional needs. | In Progress
[6 empty] | T5 | Establish a regular review cycle to keep plans current. | Not Started
P5.27.G2 ★ | FY27 | Not Started | — | Develop and implement a community paramedicine program that identifies high-utilization populations, establishes governing policies and practices, and launches a pilot program. | Matt Petitt | T1 | Identify the benefits of a community paramedicine program and research models from comparable agencies. | Not Started | Community paramedicine program operational with documented policies, a defined patient population, and at least six months of utilization and outcome data collected.
[6 empty] | T2 | Identify the areas and populations most in need and engage stakeholders interested in program development. | Not Started
[6 empty] | T3 | Establish policies and clinical practices governing program delivery. | Not Started
[6 empty] | T4 | Implement the program and begin tracking utilization and outcome data. | Not Started
FY28
P5.28.G1 ★ | FY28 | Not Started | P5.27.G2 | Analyze incident data from community paramedicine operations to identify populations where a mobile integrated health program would reduce resource utilization and improve outcomes, and establish the program framework. | Nick Satterly | T1 | Analyze incident data to identify where MIH programs would have the greatest impact on resource allocation and non-transported patient outcomes. | Not Started | MIH program framework adopted and operational with trained providers, at least one formal partner agreement in place, and baseline utilization data being tracked.
[6 empty] | T2 | Identify potential partnerships with local hospitals and third-party entities to become preferred providers for in-home care. | Not Started
[6 empty] | T3 | Establish a framework for MIH functions within the current response matrix. | Not Started
[6 empty] | T4 | Train and establish MIH-designated providers. | Not Started
P5.28.G2 | FY28 | Not Started | P5.28.G1 | Evaluate the feasibility, return on investment, and strategic placement of a specialty care transport unit within the current response model, and establish response guidelines if the program moves forward. | Nick Satterly | T1 | Identify the ROI of specialty care transport within the current system using MIH utilization data. | Not Started | A completed feasibility analysis and ROI assessment presented to command staff with a documented go or no-go recommendation.
[6 empty] | T2 | Identify strategic placement of unit or units to best serve the community within the response model. | Not Started
[6 empty] | T3 | Establish response guidelines, a framework, and clinical protocols for a specialty care transport unit. | Not Started
P5.28.G3 | FY28 | Not Started | P5.27.G2 | Strengthen relationships with local hospitals and healthcare systems to support joint education programs, MIH referral pathways, and collaborative community health initiatives. | Jay Sousa | T1 | Participate in meetings with hospital representatives to identify opportunities for joint education programs. | Not Started | At least two formal hospital partnerships documented with defined collaboration scope, and at least one joint community education event conducted.
[6 empty] | T2 | Identify potential for MIH referral partnerships with hospital and healthcare partners. | Not Started
[6 empty] | T3 | Strengthen existing relationships to improve communication and collaboration on community health initiatives. | Not Started

## P6 Infrastructure, Tech
P6 — Infrastructure, Technology, and Fiscal Stewardship
Steward: Nick Herlihy
Goal ID | Year | Status | Predecessor | Goal Statement | Owner | T# | Task | Task Status | Success Metric
FY26
P6.26.G1 ★ | FY26 | Not Started | — | Modernize apparatus and fleet maintenance tracking by implementing a system that accurately captures complaint dates, repair timelines, return-to-service data, and key performance indicators for all vehicles. | Terry Mccloud | T1 | Modernize the process for reporting mechanical issues to fleet to allow accurate tracking from complaint through return to service. | Not Started | A functional fleet tracking system capturing all defined KPIs, with a baseline year of data collected and an initial cost and downtime analysis completed.
[6 empty] | T2 | Develop a program to determine apparatus downtime and compare the PM schedule to manufacturer recommendations. | Not Started
[6 empty] | T3 | Calculate annual maintenance costs for fire suppression, EMS, and administrative vehicles and identify cost-saving opportunities. | Not Started
[6 empty] | T4 | Create KPIs including apparatus availability rate, reserve utilization, unscheduled repairs per call volume, average repair turnaround time, and parts procurement time. | Not Started
P6.26.G2 | FY26 | In Progress | — | Obtain and maintain ISO 1 rating and advance the department's CFAI accreditation through coordinated stakeholder engagement, infrastructure improvement, and documentation compliance. | Nick Herlihy | T1 | Coordinate with city directors and relevant partners on infrastructure requirements for ISO 1 maintenance. | Not Started | ISO 1 rating maintained and CFAI accreditation status advanced with all required documentation submitted on schedule.
[6 empty] | T2 | Review criteria to maintain ISO 1 and assess all needs. | Complete
[6 empty] | T3 | Advance CFAI accreditation — formalize accreditation SOG, implement processes, and gather proof of compliance. | In Progress
[6 empty] | T4 | Achieve CFAI applicant status. | Complete
[6 empty] | T5 | Identify and pursue funding sources including grants and capital budget requests. | Not Started
FY27
P6.27.G1 | FY27 | Not Started | P6.26.G1 | Analyze fleet maintenance cost and effectiveness data collected in P6.26.G1 to identify outsourcing opportunities, evaluate in-house EVT feasibility, and develop long-term cost reduction strategies. | Terry Mccloud | T1 | Analyze maintenance program effectiveness using tracking data from P6.26.G1. | Not Started | A completed fleet cost and effectiveness analysis with specific recommendations on outsourcing and EVT feasibility presented to command staff and city leadership.
[6 empty] | T2 | Identify apparatus with the highest maintenance burden and cost. | Not Started
[6 empty] | T3 | Calculate and compare the cost of outsourcing preventive maintenance for passenger vehicles against in-house alternatives. | Not Started
[6 empty] | T4 | Evaluate the feasibility of hiring an in-house Emergency Vehicle Technician. | Not Started
[6 empty] | T5 | Present findings and recommendations to city leadership. | Not Started
P6.27.G2 | FY27 | Not Started | — | Evaluate and improve interoperability between scheduling and payroll platforms, specifically CrewSense and ExecuTime, to reduce administrative correction workload and improve payroll accuracy. | Dave Ingalls | T1 | Assess the current state of data exchange between CrewSense and ExecuTime and document known gaps and errors. | Not Started | A documented reduction in payroll correction workload and measurable improvement in payroll accuracy following implementation.
[6 empty] | T2 | Engage city IT to identify integration solutions or middleware that can improve platform communication. | Not Started
[6 empty] | T3 | Implement improvements and measure impact on payroll accuracy and administrative correction workload. | Not Started
P6.27.G3 ★ | FY27 | Not Started | — | Migrate departmental records to a centralized, access-controlled digital library that meets retention requirements, with proper file mapping, access controls, and disposition of records that have met retention. | Anna Duffey | T1 | Meet with staff to develop a record inventory of all records created and maintained, and identify current storage locations. | Not Started | All active departmental records migrated to the centralized library with a documented file map, access control structure, and a completed disposition log.
[6 empty] | T2 | Work with staff to develop a record library system including file mapping, access controls, and permission structures. | Not Started
[6 empty] | T3 | Migrate records that have not met retention from shared drives and local drives to the centralized library. | Not Started
[6 empty] | T4 | Inventory electronic records that have met retention, review with staff, and complete necessary disposals with the Clerk's office. | Not Started
P6.27.G4 | FY27 | Not Started | — | Create a Historical and Archive Committee to identify, catalogue, and maintain records and other items of historical significance to the department. | Anna Duffey | T1 | Develop the committee mandate, scope, mission, goals, structure, and roles. | Not Started | Committee established with a formal mandate and at least one complete inventory of historical items with documented storage and handling procedures.
[6 empty] | T2 | Identify potential members and recruit a committee. | Not Started
[6 empty] | T3 | Develop appropriate policies including collection, access and use, preservation and storage, and digitization and backup policies. | Not Started
[6 empty] | T4 | Inventory and evaluate existing items, determine appropriate storage and handling procedures, and identify space and resources needed. | Not Started
FY29
P6.29.G1 | FY29 | Not Started | P6.27.G3 | Establish and maintain a formal periodic policy review process within PowerDMS ensuring 95% on-time completion, zero overdue reviews, and regulatory compliance across all departmental policies. | Tammie Wichers | T1 | Assign each policy to the appropriate division and subject matter expert. | Not Started | Zero overdue policy reviews in PowerDMS, 95% or higher on-time completion rate sustained, and all policies assigned to an owner and subject matter expert.
[6 empty] | T2 | Achieve Policy Review Board evaluation and approval for all policies requiring updates within 60 days of submission. | Not Started
[6 empty] | T3 | Reduce the number of overdue policy reviews in PowerDMS to zero by year end, with receipting within 14 days. | Not Started
[6 empty] | T4 | Maintain a 95% or higher on-time policy review completion rate annually. | Not Started

## Dependencies
DEPENDENCY CHAINS
★ = Gate goal — must complete before downstream goals can begin
Gate Goal | Gate Statement | Unlocks | Unlocked Statement
P1.26.G1 ★ | Evaluate the current deployment model against 36 months of incident data to identify gaps in response capability, unit utilization, and geographic coverage. | P1.27.G1 | Develop and implement a major incident response planning program covering all identified threat types within NPFR's response model, aligned to deployment gaps identified in P1.26.G1.
P1.26.G1 ★ | Evaluate the current deployment model against 36 months of incident data to identify gaps in response capability, unit utilization, and geographic coverage. | P1.27.G3 | Establish three strategically located logistics resource hubs using locker technology to improve access to EMS supplies, reserve equipment, and operational resources while reducing replenishment demands.
P1.27.G3 ★ | Establish three strategically located logistics resource hubs using locker technology to improve access to EMS supplies, reserve equipment, and operational resources while reducing replenishment demands. | P1.28.G1 | Develop and implement a logistics operational resiliency program that eliminates single-point dependencies through knowledge management, cross-training, and continuity planning across all critical logistics functions.
P2.26.G1 ★ | Identify all member development gaps, career pathways, and critical functions across the department to establish the foundation for succession and development planning. | P2.27.G1 | Develop and implement career development pathways and supporting policies for all department positions, based on the gap analysis findings from P2.26.G1.
P2.27.G1 ★ | Develop and implement career development pathways and supporting policies for all department positions, based on the gap analysis findings from P2.26.G1. | P2.27.G2 | Develop and implement a department-wide succession plan covering all positions, built through multi-level organizational input and aligned to the career pathways established in P2.27.G1.
P2.27.G1 ★ | Develop and implement career development pathways and supporting policies for all department positions, based on the gap analysis findings from P2.26.G1. | P2.27.G3 | Create a structured administrative development program that provides interested line personnel with meaningful exposure to departmental administrative functions, building internal bench strength before vacancies arise.
P2.27.G1 ★ | Develop and implement career development pathways and supporting policies for all department positions, based on the gap analysis findings from P2.26.G1. | P2.29.G1 | Pursue regional recognition as a fire training resource by establishing institutional partnerships, gaining applicable accreditation, and hosting accredited training offerings for external agencies.
P2.27.G2 ★ | Develop and implement a department-wide succession plan covering all positions, built through multi-level organizational input and aligned to the career pathways established in P2.27.G1. | P2.28.G1 | Achieve and maintain 90% or greater professional credentialing of all applicable positions aligned with CFAI credentialing categories, integrated into the succession plan and Officer Development Program.
P3.26.G1 ★ | Identify and assess department health and wellness needs through workforce survey, industry comparison, and facility evaluation, and report findings to inform program development. | P3.26.G2 | Develop and implement programs addressing behavioral health, PTSD support, cancer prevention, nutrition, fitness, and chaplain services, based on the findings from P3.26.G1.
P4.26.G1 ★ | Gather and organize incident and community risk data across five task areas to establish a baseline for all CRR program development. | P4.27.G1 | Evaluate and rank the community risk data gathered in P4.26.G1 to identify the highest-priority program areas and determine staffing, resource, and policy requirements for program development.
P4.27.G1 ★ | Evaluate and rank the community risk data gathered in P4.26.G1 to identify the highest-priority program areas and determine staffing, resource, and policy requirements for program development. | P4.28.G1 | Develop and launch a comprehensive community risk reduction program with targeted interventions in fire prevention, drowning prevention, fall prevention, CPR training, and severe weather preparedness.
P4.28.G1 ★ | Develop and launch a comprehensive community risk reduction program with targeted interventions in fire prevention, drowning prevention, fall prevention, CPR training, and severe weather preparedness. | P4.28.G2 | Establish a community outreach team of 10 to 15 trained firefighters who can support public education presentations and CRR events across the community.
P4.28.G1 ★ | Develop and launch a comprehensive community risk reduction program with targeted interventions in fire prevention, drowning prevention, fall prevention, CPR training, and severe weather preparedness. | P4.29.G1 | Expand upon the three most successful CRR programs based on effectiveness data, improve weaker programs, and establish a state-level presence advocating for residential fire sprinkler requirements.
P5.27.G2 ★ | Develop and implement a community paramedicine program that identifies high-utilization populations, establishes governing policies and practices, and launches a pilot program. | P5.28.G1 | Analyze incident data from community paramedicine operations to identify populations where a mobile integrated health program would reduce resource utilization and improve outcomes, and establish the program framework.
P5.27.G2 ★ | Develop and implement a community paramedicine program that identifies high-utilization populations, establishes governing policies and practices, and launches a pilot program. | P5.28.G3 | Strengthen relationships with local hospitals and healthcare systems to support joint education programs, MIH referral pathways, and collaborative community health initiatives.
P5.28.G1 ★ | Analyze incident data from community paramedicine operations to identify populations where a mobile integrated health program would reduce resource utilization and improve outcomes, and establish the program framework. | P5.28.G2 | Evaluate the feasibility, return on investment, and strategic placement of a specialty care transport unit within the current response model, and establish response guidelines if the program moves forward.
P6.26.G1 ★ | Modernize apparatus and fleet maintenance tracking by implementing a system that accurately captures complaint dates, repair timelines, return-to-service data, and key performance indicators for all vehicles. | P6.27.G1 | Analyze fleet maintenance cost and effectiveness data collected in P6.26.G1 to identify outsourcing opportunities, evaluate in-house EVT feasibility, and develop long-term cost reduction strategies.
P6.27.G3 ★ | Migrate departmental records to a centralized, access-controlled digital library that meets retention requirements, with proper file mapping, access controls, and disposition of records that have met retention. | P6.29.G1 | Establish and maintain a formal periodic policy review process within PowerDMS ensuring 95% on-time completion, zero overdue reviews, and regulatory compliance across all departmental policies.

## Changelog
CHANGELOG
Timestamp | Type | Goal | Detail
2026-06-09T00:00:00 | migration |  | Initial migration to P#.YY.G# ID format. All goal IDs updated, predecessor references updated, statuses carried forward from vendor workbook baseline.